## Index
DVDAddin — Command practice workbook
Each sheet holds exactly the data shown in the guide pictures: cell addresses, column headers and formats match every step. Open the guide (last column), switch to the matching sheet and follow along. Save a copy first — a few commands work on the whole workbook (renaming, hiding, numbering or stripping accents from sheet names).
No. | Tab | Group | Command | Practice sheet | Do this first | Guide
1 | DVD Cons | Schedule | Gantt Chart | Gantt Chart | Open the schedule sheet and put the cursor in a cell of the task table, e.g. the last row — the add-in finds the header row (Duration / Start / Finish) and the data range by itself. | Open the guide
2 | DVD Cons | Schedule | Auto Calc | Auto Calc | The button lights up while it is ON; Excel's status bar confirms it for about 6 seconds . Now try an edit: type a new duration for Excavate foundation pits — from 6 down to 4 days — and press Enter. | Open the guide
3 | DVD Cons | Schedule | Auto Draw | Auto Draw | The button lights up while it is ON; the status bar confirms it for about 6 seconds . Now edit as usual — e.g. Excavate foundation pits hits groundwater, so its duration goes from 6 to 8 days . | Open the guide
4 | DVD Cons | Schedule | Update schedule (data date) | Update schedule (data date) | Bring the actuals up to the report date: Actual Start, Actual Finish and % complete of each task . Here the report date is Wednesday 21/10/2026: Pile cap rebar and formwork is only 25% done, and Prefabricate column starter bars was due to start on 15/10 but has not started. | Open the guide
5 | DVD Cons | Schedule | Update Status | Update Status | Open the schedule sheet to assess. It needs Duration / Start / Finish / Complete columns ; with Actual Start / Actual Finish you also get Δ Finish, Status and Forecast; with BAC / EV (here in million VND) you also get PV, SV and SPI. | Open the guide
6 | DVD Cons | Schedule | Setup | — (no sample data needed) |  | Open the guide
7 | DVD Cons | Schedule | Gantt Tpl | — (no sample data needed) |  | Open the guide
8 | DVD Cons | Schedule | Constraints | Constraints | Open the schedule sheet and select the task row(s) to constrain — here Erect tower crane, because the crane pad is only handed over on 02/11/2026. With no row of the data area selected, the command just reminds you and stops. | Open the guide
9 | DVD Cons | Schedule | Header Language | Header Language | Open the schedule sheet whose headers you want to switch — e.g. a sheet just imported from MS Project, with English headers . | Open the guide
10 | DVD Cons | Schedule | Export XML (P6/MSP) | Export XML (P6-MSP) | Open the schedule sheet to export (it must be a worksheet). Let Auto Calc finish a pass first so the dates are current — the command only reads, it never changes the sheet. | Open the guide
11 | DVD Cons | Schedule | Import XML (P6/MSP) | — (no sample data needed) |  | Open the guide
12 | DVD Cons | Schedule | Import .xer (P6) | — (no sample data needed) |  | Open the guide
13 | DVD Cons | Schedule | AI Gantt Builder | AI Gantt Builder | Open the bill-of-quantities sheet and select the BoQ range including its header row — column 1 code, column 2 item name, column 3 unit, column 4 quantity. | Open the guide
14 | DVD Cons | Schedule | Schedule Recovery | Schedule Recovery | Open the schedule sheet that has Start / Finish / Complete (%) columns , with % complete updated to the cut-off date. | Open the guide
15 | DVD Cons | Schedule | Health Check | Health Check | Open the schedule to assess: it has Activity IDs, Predecessors links and actual dates. Run Auto Calc first so the Total Float column is filled — without it the Negative / High float checks are skipped. | Open the guide
16 | DVD Cons | Schedule | EVM Report | EVM Report | On the schedule sheet, update Complete (%) and the actual cost AC up to the cut-off date; the BAC column holds each activity's budget (no BAC column yet? add a BAC column to the table first). | Open the guide
17 | DVD Cons | Schedule | Variance Dashboard | Variance Dashboard | Open the schedule sheet with up-to-date actual dates , % complete and the BAC / AC columns — the dashboard needs both the schedule and the cost side. | Open the guide
18 | DVD Cons | Schedule | 2-Week Lookahead | 2-Week Lookahead | Open the schedule sheet with actual dates and % complete updated to today. Activity A3005 was due on 18/09 but is only 80% done — overdue work like this still makes it into the plan. | Open the guide
19 | DVD Cons | Schedule | 3-Week Lookahead | 3-Week Lookahead | Open the schedule sheet with actual dates and % complete updated to today. Activity A3005 was due on 18/09 but is only 80% done — overdue work like this still makes it into the plan. | Open the guide
20 | DVD Cons | Schedule | Schedule (custom range) | Schedule (custom range) | Open the source schedule sheet with Activity ID / Name and the Start / Finish columns . The command does not re-run CPM, so run Auto Calc first if you just changed the logic. | Open the guide
21 | DVD Cons | Schedule | Baseline | — (no sample data needed) |  | Open the guide
22 | DVD Cons | Schedule | Snapshot | Snapshot | Bring the schedule up to the weekly cut-off: Complete (%) and the actual cost AC (the BAC column is needed for SPI / CPI in the snapshot), then run Auto Calc. | Open the guide
23 | DVD Cons | Schedule | Snapshot Trend | — (no sample data needed) |  | Open the guide
24 | DVD Cons | Schedule | Manpower | Manpower | Open the schedule sheet with a Manpower column — the crew size per day for each activity (without it the command counts concurrent activities instead). Run Auto Calc so the dates are current. | Open the guide
25 | DVD Cons | Schedule | Level resources | Level resources | Open the schedule sheet with a Predecessors column (so the build sequence is kept) and a Manpower column . | Open the guide
26 | DVD Cons | Schedule | Cash-flow | Cash-flow | Open the schedule sheet with a BAC (budget) for each activity and complete Start / Finish dates; run Auto Calc so the dates are current. | Open the guide
27 | DVD Cons | Optimizer | Rebar Cut | Rebar Cut | Open the workbook that holds a four-column cut list Ø (mm) · Length (mm) · Quantity · Marks — the 2_CutList sheet written by Bar schedule → Export cut list, or the Cutting Tpl file. Rows below the coil threshold (10 mm by default) are not cut, only totalled in metres and kg. | Open the guide
28 | DVD Cons | Optimizer | Manual schedule | — (no sample data needed) |  | Open the guide
29 | DVD Cons | Optimizer | Bar schedule | Bar schedule | Select the rebar dimension table, header row included . The shape column takes either a code (00, 21, 51…) or a word (straight, L, đai); only the diameter column is mandatory. | Open the guide
30 | DVD Cons | Optimizer | Bar Cut 1D | Bar Cut 1D, Bar Cut 1D · CatThanh_Thanh | Enter the pieces to cut on the CatThanh_Phoi sheet — if the sheet does not exist yet, create it with Bar Tpl. Example: frame and bracing in 50×50 box section for a working platform. | Open the guide
31 | DVD Cons | Optimizer | Panel Cut 2D | Panel Cut 2D, Panel Cut 2D · CatTam_Tam | Enter the pieces to cut on the CatTam_Phoi sheet — if the sheet does not exist yet, create it with Panel Tpl. Example: film-faced plywood formwork for one floor; set Rotate (1/0) to 0 for the edge boards that must keep the grain direction. | Open the guide
32 | DVD Cons | Optimizer | Cutting Tpl | Cutting Tpl | Go to the 2_CatThep sheet: four columns Ø (mm) · Chiều dài (mm) · Số lượng · Ký hiệu (diameter, length, quantity, mark) — the file itself is in Vietnamese. The tinted rows are sample data, as the note on the right says : clear them and enter your cut list, or paste it from Bar schedule → Export cut list. | Open the guide
33 | DVD Cons | Optimizer | Bar Tpl | Bar Tpl | The add-in adds two sheets to the open workbook (with no workbook open it creates a new one) and confirms ✓ Bar-cut template ready. CatThanh_Phoi is the list of pieces to cut — Length · Qty · Material · Label · Priority, with 4 sample rows ; pieces with a higher Priority are placed first. A sheet that already has something in A1 is left untouched. | Open the guide
34 | DVD Cons | Optimizer | Panel Tpl | Panel Tpl | Clear the sample rows and enter the pieces to cut in CatTam_Phoi in the column order shown — here 8 mm glass for a curtain wall. Set Rotate (1/0) to 0 for directional glass, grained board or ribbed sheet; the Band / Grind columns list the edges to band / grind (T B L R) — leave them empty if none. | Open the guide
35 | DVD Cons | QAQC and Diary | New Diary | New Diary | Prepare the work-item catalog : one row per task with start, finish, acceptance date, description and (optionally) rest days. Put the diary period start and end date in two separate cells. The data range must include the header row — the add-in skips the first row of the range. | Open the guide
36 | DVD Cons | QAQC and Diary | Export Category | Export Category | The acceptance log has many columns, but the form for the supervision consultant needs only work item, location, date and record number. Identify the data range — data rows only, not the header row (every row with text in the base column is exported). A group row such as "A. SUBSTRUCTURE" has an empty work-item cell, so it is not exported. | Open the guide
37 | DVD Cons | QAQC and Diary | Pick Rest Days | Pick Rest Days | In the work-item catalog, select the rest-days cell of the task — select several cells if several tasks stop on the same days (up to 500 cells). | Open the guide
38 | DVD Cons | QAQC and Diary | Work Record Tpl | Work Record Tpl | The add-in opens the template FormNTCV.xlsx from the add-in folder C:\DVDAddin\Template\ (failing that, from a Template\ folder next to the open workbook; if neither exists it lists the paths it searched). Go to sheet TTC and fill in the general information : every form in the file takes the project, works, package and parties from here, and Tỉnh thành (province) starts the "…, ngày … tháng … năm …" date line of the records. | Open the guide
39 | DVD Cons | QAQC and Diary | Material Record Tpl | Material Record Tpl | The add-in opens the template FormNTVL.xlsx from the add-in folder C:\DVDAddin\Template\ (failing that, from a Template\ folder next to the open workbook; if neither exists it lists the paths it searched). Go to sheet TTC and fill in the general information : every form in the file takes the project, works, package and parties from here, and Tỉnh thành (province) starts the "…, ngày … tháng … năm …" date line of the records. | Open the guide
40 | DVD Cons | QAQC and Diary | Diary Template | Diary Template, DATA | The add-in opens the template FormNKCT.xlsx from C:\DVDAddin\Template\ (or a Template\ folder next to the open workbook) on sheet NKCT — the diary page for one day. Every cell on the page comes from sheet DATA: the date , weather, manpower and equipment , materials in and out, work carried out and accepted that day. The date line uses a cell format with the place name "Tỉnh/TP" built in — change it in Format Cells for your project. | Open the guide
41 | DVD Cons | QAQC and Diary | Test Plan | Test Plan | Select the cells that hold material names (for example the item column of a bill of quantities) . | Open the guide
42 | DVD Cons | QAQC and Diary | Acceptance Plan | Acceptance Plan | Open the sheet that holds the schedule. The add-in finds the header row with a Task Name column and Start / Finish (plus Activity ID and Level if present) ; every task row below it becomes one acceptance-plan row. | Open the guide
43 | DVD Cons | QAQC and Diary | Acceptance Record | Acceptance Record | Open the Ke hoach NT … sheet made by the Acceptance command and select the work rows to accept — Ctrl-select separate blocks if needed. The Applicable standard column is copied into the basis of acceptance, so review it and correct it to the actual standard numbers first. | Open the guide
44 | DVD Cons | QAQC and Diary | Punch list | — (no sample data needed) |  | Open the guide
45 | DVD Cons | QAQC and Diary | RFI | — (no sample data needed) |  | Open the guide
46 | DVD Cons | QAQC and Diary | Submittals | — (no sample data needed) |  | Open the guide
47 | DVD Cons | QS | AI Construction Estimate | AI Construction Estimate | Select the items to price, covering the item name, unit and (if available) quantity columns . Leave the price, source and note columns on the right empty. | Open the guide
48 | DVD Cons | QS | Interim Payment | Interim Payment | Select the contract bill of quantities, including its header row . The % done (cum.) column is the progress you update before each payment period. | Open the guide
49 | DVD Cons | QS | Compare BoQ | Compare BoQ | Both BoQ versions must share the same column layout, e.g. the Tender and Measured sheets in one workbook: column B holds the code used as the match key and column E the quantity . No selection is needed. | Open the guide
50 | DVD Cons | QS | Price adjustment | Price adjustment | Select the table of materials eligible for adjustment, including its header row : material name, quantity, base contract price and price at the adjustment date. | Open the guide
51 | DVD Cons | QS | Estimate bridge | Estimate bridge | In the estimating software, export the estimate to Excel. The export usually has a few project-name lines, a column-heading row , chapter rows and subtotal rows — no clean-up is needed, and the file does not have to be open. | Open the guide
52 | DVD Cons | QS | PDF takeoff | — (no sample data needed) |  | Open the guide
53 | DVD Cons | QS | Compare drawings | — (no sample data needed) |  | Open the guide
54 | DVD Cons | QS | Data query | Data query | Select the cell that will receive the result — here the foundation concrete quantity in the summary table. | Open the guide
55 | DVD Cons | QS | Variation Register | Variation Register | Select the takeoff of the variation items, including the header row . Quantities are positive for additions, negative for omissions . | Open the guide
56 | DVD Cons | Connection | Connect | — (no sample data needed) |  | Open the guide
57 | DVD Cons | Connection | Disconnect | — (no sample data needed) |  | Open the guide
58 | DVD Cons | Connection | Send Format | Send Format | While in a teamwork session (the Connect button reads Joined · …), format the range the way you want on your machine, then select exactly that range — e.g. the header band A5:G5 of the Tong hop sheet . | Open the guide
59 | DVD Cons | Connection | Admin | — (no sample data needed) |  | Open the guide
60 | DVD Cons | Quick | Find Cmd | — (no sample data needed) |  | Open the guide
61 | DVD Addin | Text and Number | Numbering | Numbering | Select the No. column to number . The merged cell A5:A7 counts as one cell; the hidden row (row 9, e.g. filtered out) is skipped. | Open the guide
62 | DVD Addin | Text and Number | Roman | Roman | Select the cells to fill with Roman numerals — here the No. column of the main sections . | Open the guide
63 | DVD Addin | Text and Number | Upper letters | Upper letters | Select the column to fill with letters . The merged cell A6:A7 (one appendix holding two documents) counts as one cell. | Open the guide
64 | DVD Addin | Text and Number | Lower letters | Lower letters | Select the No. cells of the detail layers under item 2 . | Open the guide
65 | DVD Addin | Text and Number | Assign Level | Assign Level | Prepare the table: fill the description column with one colour per level ; build a colour legend, one cell per level, top→bottom = level 1, 2, 3 ; keep a Level column as the rightmost column for the result . | Open the guide
66 | DVD Addin | Text and Number | Filled circle | Filled circle | Select the cells that need the bullet . In a multi-line cell (line breaks typed with Alt+Enter) every line gets the bullet. | Open the guide
67 | DVD Addin | Text and Number | Filled star | Filled star | Select the cells to highlight — here the three hold points (H) of the ITP . | Open the guide
68 | DVD Addin | Text and Number | Minus | Minus | Select the cells that need the bullet — here two cells listing materials, one per line . | Open the guide
69 | DVD Addin | Text and Number | Filled diamond | Filled diamond | Select the cells that need the bullet — here the milestone column . | Open the guide
70 | DVD Addin | Text and Number | Plus | Plus | Select the cells that need the bullet — here the variation items . | Open the guide
71 | DVD Addin | Text and Number | Asterisk | Asterisk | Select the notes cell under the table — a merged cell with one condition per line . | Open the guide
72 | DVD Addin | Text and Number | Checkbox | Checkbox | Select the items to turn into a checklist . | Open the guide
73 | DVD Addin | Text and Number | Checked | Checked | Select the lines that are done — here the three documents already submitted . | Open the guide
74 | DVD Addin | Text and Number | Rejected | Rejected | Select the items that failed . | Open the guide
75 | DVD Addin | Text and Number | Remove bullets | Remove bullets | Select the cells whose bullets (●, −, ★, ☐…) you want to remove . | Open the guide
76 | DVD Addin | Text and Number | Number list | Number list | Select the cells to number . A multi-line cell (Alt+Enter) gets one number per line. | Open the guide
77 | DVD Addin | Text and Number | Roman list | Roman list | Select the main section cells to number in Roman numerals . | Open the guide
78 | DVD Addin | Text and Number | Upper letters list | Upper letters list | Select the section cells to letter . | Open the guide
79 | DVD Addin | Text and Number | Lower letters list | Lower letters list | Select the sub-task cells to letter . | Open the guide
80 | DVD Addin | Text and Number | Remove list numbering | Remove list numbering | Select the cells whose numbering prefix you want to remove — here the numbers went wrong after a row was inserted (two items numbered 3) . | Open the guide
81 | DVD Addin | Text and Number | Multilevel 1.1.1 | Multilevel 1.1.1 | Build the outline with Increase Indent on the Home tab: the smallest indent is level 1, the next one level 2… Then select the whole item column, starting from the top level . | Open the guide
82 | DVD Addin | Text and Number | Remove multilevel numbering | Remove multilevel numbering | Select the cells carrying multilevel numbers — usually before renumbering after items were inserted . | Open the guide
83 | DVD Addin | Text and Number | Sentence case | Sentence case | Select the text cells to normalize, for example a work-description column typed in mixed case with extra spaces . | Open the guide
84 | DVD Addin | Text and Number | UPPERCASE | UPPERCASE | Select the cells to convert to upper case . | Open the guide
85 | DVD Addin | Text and Number | lowercase | lowercase | Select the cells to convert to lower case, for example a list of work items received in ALL CAPS or mixed case . | Open the guide
86 | DVD Addin | Text and Number | Proper Case | Proper Case | Select the column to normalize, for example the name / company column of a site manpower list typed in mixed case . | Open the guide
87 | DVD Addin | Text and Number | SMART case (AI) | SMART case (AI) | The command needs an AI service and API key set in Preferences. Select the text cells that were typed without proper capitals . | Open the guide
88 | DVD Addin | Text and Number | Italic | Italic | Select the bilingual cells, each holding two lines separated by Alt+Enter: Vietnamese on top, English below . | Open the guide
89 | DVD Addin | Text and Number | Text Reverse | Text Reverse | Select the cells to reverse, for example a list written as "Work item - Code" where you want the norm code first . | Open the guide
90 | DVD Addin | Text and Number | Font Change | Font Change | Select the bilingual cells whose second part needs another font, for example a header row written as Vietnamese / English . | Open the guide
91 | DVD Addin | Text and Number | Remove extra spaces | Remove extra spaces | Select the text to clean, for example a work-item column pasted from an estimate with extra spaces at the start, the end and in between . The =LEN(B2) column shows spaces you cannot see. | Open the guide
92 | DVD Addin | Text and Number | Add text | Add text | Select the cells that need the extra text, for example the work items of footing M1 that need the item code as a prefix . | Open the guide
93 | DVD Addin | Text and Number | Remove accents | Remove accents | Select the accented text cells, for example item names that will be used as folder names for the acceptance records . | Open the guide
94 | DVD Addin | Text and Number | Add accents (AI) | Add accents (AI) | The command needs an AI service and API key configured in Preferences. Select the column typed without Vietnamese accents, for example a site diary typed on a phone ; cells that already have accents are skipped. | Open the guide
95 | DVD Addin | Text and Number | Auto format | Auto format | Select the quantity and date columns that are stored as text (left-aligned) — which is why the SUM in the Total row returns 0 . | Open the guide
96 | DVD Addin | Text and Number | Superscript | Superscript | Select the unit column of the bill of quantities (or any range that contains units) . | Open the guide
97 | DVD Addin | Text and Number | Subscript | Subscript | Select the cells holding chemical formulas, for example a list of mixing-water components and test items — cells where formulas sit inside a sentence are fine too. | Open the guide
98 | DVD Addin | Text and Number | Bulk find / replace… | Bulk find - replace… | Open the sheet to fix. In the estimate below several lines use the abbreviation RC , which must read "Reinforced concrete" in the printed submission. | Open the guide
99 | DVD Addin | Text and Number | Smart Data Cleaning… | Smart Data Cleaning… | Select the whole table to clean, header row included . The example is a material list merged from several files: stray spaces, inconsistent capitals and two rows entered twice. | Open the guide
100 | DVD Addin | Text and Number | Encoding | Encoding | Select the range to convert . This old quantity table was typed in the VNI-Times font; on a machine without that font the text shows up as garbled characters. | Open the guide
101 | DVD Addin | Text and Number | To Unicode | To Unicode | Select the cells with garbled text . This table was typed in the .VnTime font (TCVN3); opened on a machine without that font it shows characters like C«ng t¸c. | Open the guide
102 | DVD Addin | Text and Number | To VNI | To VNI | Select the description column that must go into a template using the VNI-Times font . | Open the guide
103 | DVD Addin | Text and Number | To TCVN3 | To TCVN3 | Select the work-description column that goes into an old template using the .VnTime font . | Open the guide
104 | DVD Addin | Text and Number | Translate | Translate | Select the cells to translate — here the description column of a bill of quantities written in English by a foreign consultant. | Open the guide
105 | DVD Addin | Text and Number | Quick Input | Quick Input | Put the cursor in the cell to fill, below a column that already has data — here the Work item cell of a new diary row. | Open the guide
106 | DVD Addin | Text and Number | Auto-suggest on cell select | Auto-suggest on cell select | The button turns on and the status bar shows Quick Input: ON for about 5 seconds . From now on, selecting a cell in the trigger column of a rule set up in Configure source ranges… pops the suggestion window up by itself: type to filter, Enter to insert, Esc to dismiss. | Open the guide
107 | DVD Addin | Text and Number | Configure source ranges… | Configure source ranges… | Prepare the catalogue table that will be the source, with a header row — here the Catalogue sheet with Code, Material, Unit, Unit price. | Open the guide
108 | DVD Addin | Cells and Rows | Insert Rows | Insert Rows | Click a cell in the row where the new rows should go — they are inserted above that row. For example, to add 3 items before row 6, select any cell in row 6, such as B6 . | Open the guide
109 | DVD Addin | Cells and Rows | Insert Columns | Insert Columns | Click a cell in the column that the new columns should go before. For example, to add 4 columns for 4 payment rounds before Contract qty, select cell D3 . | Open the guide
110 | DVD Addin | Cells and Rows | Insert and Copy | Insert and Copy | The first range box asks Select source area: drag over the template rows — here A8:D10 with Materials / Labour / Plant — then click OK. | Open the guide
111 | DVD Addin | Cells and Rows | Delete blanks | Delete blanks | The range box asks Select data range to delete blank rows: drag over the table, here A4:D12 , then click OK. Every row of the range with no data at all will be deleted. | Open the guide
112 | DVD Addin | Cells and Rows | Delete hidden rows | Delete hidden rows | Hide the rows you do not want to keep — usually with AutoFilter. For example, filter the Package column to Steelwork only: the rows of other packages become hidden. Work on a copy of the original file. | Open the guide
113 | DVD Addin | Cells and Rows | Delete unused formats | Delete unused formats | Open the sheet to clean — the command works on the active sheet only, no selection needed. Here the real data ends at E8, but borders and fills run on beyond it , so Ctrl+End jumps far away, the file is heavy and prints blank pages. | Open the guide
114 | DVD Addin | Cells and Rows | Delete error Defined Names | — (no sample data needed) |  | Open the guide
115 | DVD Addin | Cells and Rows | Strip junk styles | — (no sample data needed) |  | Open the guide
116 | DVD Addin | Cells and Rows | Merge keep data | Merge keep data | Select the cells to merge, for example the three description lines B4:B6 . You can Ctrl-select several separate ranges — each one becomes its own merged cell. | Open the guide
117 | DVD Addin | Cells and Rows | Merge similar | Merge similar | Select the range to merge — preferably a single column, such as the member column A4:A9 . A multi-column range is walked row by row, so cells can get merged with their neighbours. | Open the guide
118 | DVD Addin | Cells and Rows | Merge rows by key | Merge rows by key | The range box asks Please select a range: drag over the data block without the header row, for example A4:C9 , then click OK. The first column is always the key; the range needs at least 2 columns × 2 rows. | Open the guide
119 | DVD Addin | Cells and Rows | Auto group | Auto group | The table needs a column of outline numbers (1, 1.1, 1.1.1…) or integer levels (1, 2, 3). Select that column first, for example A4:A13 , so the window fills the range in for you. | Open the guide
120 | DVD Addin | Cells and Rows | AutoFit merged | AutoFit merged | Select the range holding the merged cells to fit — the whole form is fine, plain rows and merged rows alike . Here the merged cells B4:F4 and B8:F8 show only one line of text, so the rest would be lost in print. | Open the guide
121 | DVD Addin | Cells and Rows | Select visible | Select visible | Filter (AutoFilter) or hide rows as usual, then select the data range to work on — for example a bill of quantities filtered to Superstructure (rows 4–5, 8 and 11 are hidden): select A3:E11 . | Open the guide
122 | DVD Addin | Cells and Rows | Copy/Paste visible | Copy-Paste visible | Filter or hide rows on the target sheet (and on the source sheet if needed) so only the part to process is visible — for example filter the Level column of the Acceptance sheet to Level 5: the Level 4 rows (4, 6, 8, 10) are hidden. | Open the guide
123 | DVD Addin | Cells and Rows | Join Text | Join Text | Select the cells whose values you want to join, for example the form sheet codes B2:B4 . Blank cells in the range are skipped. | Open the guide
124 | DVD Addin | Cells and Rows | Join Merged | Join Merged | Select the range holding the merged cells whose addresses you need — here the two cells that change per batch print, Work item and Location: B4:D5 . Empty cells are skipped. | Open the guide
125 | DVD Addin | Formula | Formula View | Formula View, KL Tang 4, KL Tang 5 | Select the cell whose formula you want to check — for example a summary quantity that returns 0 although the detail sheet has figures. The long formula in the formula bar is hard to read by eye. | Open the guide
126 | DVD Addin | Formula | Lookup Trace | Lookup Trace, RATES | Select one cell that holds a lookup formula — for example a unit rate pulled with VLOOKUP from the rates sheet. The formula shows in the formula bar . | Open the guide
127 | DVD Addin | Formula | Dependents | Dependents | Select the cell to check — for example the machine-shift factor on the parameters sheet. The command always tracks the active cell, not the whole selection. | Open the guide
128 | DVD Addin | Formula | Autosum | Autosum | Prepare a table with a key column — here the section column is filled only on summary rows and left blank on detail rows — and the data column to sum , both with the same rows. | Open the guide
129 | DVD Addin | Formula | Fill Results | Fill Results | Prepare a table with a description column (the calculation text) and a matching result column , row by row. | Open the guide
130 | DVD Addin | Formula | Direct Ref | Direct Ref, DON GIA | Prepare the source range : its first column is the item code (key), its last column receives the unit-rate formula. The target is the rates table on sheet DON GIA, with codes in column A and rates in column D. | Open the guide
131 | DVD Addin | Formula | Rounding Func | Rounding Func | Select the cells whose formulas you want to round — here a quantity column that shows too many decimals. | Open the guide
132 | DVD Addin | Formula | Lock Ref | Lock Ref, BANGTHEP | Select the formula cells whose reference style you want to change — for example the rebar weight column before copying the whole block to a summary sheet without the references shifting. The formulas currently use relative references . | Open the guide
133 | DVD Addin | Formula | Error Check | Error Check | Select the formula cells that show Excel's green warning triangles — for example an amount column whose section subtotal rows use a different formula from the rows around them, so Excel flags an “inconsistent formula”. | Open the guide
134 | DVD Addin | Graphics | Color Shapes | Color Shapes | On the sheet whose plan is drawn with named shapes (O_A1, O_A2…), build a mapping table: first column = shape name, second column = colour code (Excel RGB number or #RRGGBB) — here the code is computed by a formula from the status column . | Open the guide
135 | DVD Addin | Graphics | Color Rects | Color Rects | Prepare a range whose values are numeric RGB colour codes — here a zone × week grid where a formula turns the status into a colour code (grey = not yet, yellow = pour week, green = poured) . | Open the guide
136 | DVD Addin | Graphics | List Shapes | List Shapes | Open the sheet that holds the shapes (here: the level 3 plan with a title box and a group of 6 slab bays) and select an empty starting cell — the list runs down from this cell. | Open the guide
137 | DVD Addin | Graphics | Rename Shapes | Rename Shapes | On the sheet that holds the shapes, build a two-column table: left = old name, right = new name . Get the old names quickly with List Shapes. | Open the guide
138 | DVD Addin | Graphics | Number Shapes | — (no sample data needed) |  | Open the guide
139 | DVD Addin | Graphics | Get Position | Get Position | Type or paste the names of the shapes into a column, then select the cells holding those names . | Open the guide
140 | DVD Addin | Graphics | Linked Labels | Linked Labels | The footings on the drawing are shapes named 1, 2, 3… (quickly set with Number Shapes). Next to it is the tracking table: select a range whose first column = shape names and last column = the cells to place (here the pour date) — columns in between are ignored . | Open the guide
141 | DVD Addin | Graphics | Make Labels Static | — (no sample data needed) |  | Open the guide
142 | DVD Addin | Graphics | Footing shapes from DWG | — (no sample data needed) |  | Open the guide
143 | DVD Addin | Graphics | Pile shapes from DWG | — (no sample data needed) |  | Open the guide
144 | DVD Addin | Graphics | Column/wall shapes from DWG | — (no sample data needed) |  | Open the guide
145 | DVD Addin | Graphics | Plan progress | Plan progress | The add-in creates the sheet TĐ Pile plan right after the plan: a No. ¦ Shape name ¦ Status ¦ Date ¦ Note table with names in natural order. Pick each row's status from the drop-down and fill in dates if needed. The legend on the right : each colour is the fill of the Colour cell (change it with Home ▸ Fill); Count and Share are computed automatically. | Open the guide
146 | DVD Addin | Graphics | Get Color Code | Get Color Code | The command writes the colour code over the selected cells themselves, so first copy the coloured cells to a spare column — for example copy the Standard colour column to column D . | Open the guide
147 | DVD Addin | Graphics | Auto Click | Auto Click | Each click becomes a row on the separate AutoClick sheet (created if missing). Edit X / Y or Wait (ms) — the delay before that row's click — directly to fine-tune . | Open the guide
148 | DVD Addin | Graphics | Pictures | Pictures | The Select target range box appears: drag over the picture cells C4:C15 — each merged area counts as one slot — and click OK. In the next box, Enter padding between image and cell border, keep 2 (points) and click OK. | Open the guide
149 | DVD Addin | Graphics | Insert by Name | Insert by Name | In Cells with image basenames, drag over the code column B4:B7 and click OK. In Cells to insert images into, drag over C4:C7 — or just the first cell C4, the command then moves down one merged area at a time — and click OK. In Spacing 2-5, keep 2 and click OK. | Open the guide
150 | DVD Addin | Graphics | Pic Comment | Pic Comment | Click the cell that should carry the picture, for example the remark cell F4 of slab bay A-B . The command uses only the active cell, even if a whole range is selected. | Open the guide
151 | DVD Addin | Graphics | Comment by Name | Comment by Name | Select the cells that hold the picture names — for example the inspection-record numbers A4:A8 . Each value is the picture's file name, usually without extension (NT-501). | Open the guide
152 | DVD Addin | Graphics | Move/Resize | Move-Resize | Click the misplaced picture — here the photo of footing M3 has drifted out of C8:C11 and covers column D. You must select the picture/shape object, not a cell. | Open the guide
153 | DVD Addin | Graphics | Capture and Annotate | Capture and Annotate | Click the cell that will receive the picture, for example B9 of the meeting minutes — the Insert into Excel button places the picture at the active cell. | Open the guide
154 | DVD Addin | Graphics | Revision Cloud | — (no sample data needed) |  | Open the guide
155 | DVD Addin | Graphics | Polygon Cloud | Polygon Cloud | Click the six corners along the L-shaped strengthening zone in turn → — the scallops follow the cursor from the third point. Hold Shift to keep the current edge at 0°/45°/90°; Backspace removes a wrong last point, Esc discards the whole shape. | Open the guide
156 | DVD Addin | Graphics | Cloud Around Selection | Cloud Around Selection | Select row 5, then hold Ctrl and add rows 8 and 11 — the three blocks are the quantity lines that changed since the last payment. (With shapes or pictures selected, each one gets a cloud around its visible frame and stays unchanged.) | Open the guide
157 | DVD Addin | Graphics | Convert to Cloud | — (no sample data needed) |  | Open the guide
158 | DVD Addin | Graphics | Arrow | — (no sample data needed) |  | Open the guide
159 | DVD Addin | Graphics | Text Note | — (no sample data needed) |  | Open the guide
160 | DVD Addin | Graphics | Sticky Note | — (no sample data needed) |  | Open the guide
161 | DVD Addin | Graphics | Callout | — (no sample data needed) |  | Open the guide
162 | DVD Addin | Graphics | Cloud Options… | — (no sample data needed) |  | Open the guide
163 | DVD Addin | File and Print | File List | File List | Click the cell where the list should start, for example A5 on the register sheet . | Open the guide
164 | DVD Addin | File and Print | Combine files | — (no sample data needed) |  | Open the guide
165 | DVD Addin | File and Print | Split table | Split table | Select the table to split, including its header row . The Package column will be the key column. | Open the guide
166 | DVD Addin | File and Print | Compare sheets | Compare sheets | The bottom of the window reports Found 8 differences: 3 changed, 0 only in A, 5 only in B. The details are on the new Compare sheet in file B: a summary of both sheets and the number of cells compared , then one row per difference — cell address, value in A, value in B and kind . | Open the guide
167 | DVD Addin | File and Print | Merge tables | Merge tables, Rates (2) | The main table has a Code column, but Unit is still empty and there is no Unit rate. The company price list (also keyed by code) is on the Rates sheet — it may also be in another open workbook. | Open the guide
168 | DVD Addin | File and Print | Rename Files | Rename Files | Build a two-column table: the left column holds the old file name, the right column the new file name (preferably with the extension). Leave the column right of the table empty — the command writes each row's status there. The range to pick is the data only, without the header row . | Open the guide
169 | DVD Addin | File and Print | File Tree | — (no sample data needed) |  | Open the guide
170 | DVD Addin | File and Print | Create Hyperlink | Create Hyperlink | Select the cells that hold file paths as plain text . | Open the guide
171 | DVD Addin | File and Print | Folder Tree | — (no sample data needed) |  | Open the guide
172 | DVD Addin | File and Print | Create Folder | Create Folder | Type the folder list from row 2 down : column A = level 1, column B = level 2, column C = level 3… An empty cell keeps the parent from the row above, so you never repeat a parent name. Leave A1 empty — the command writes the parent folder path there. | Open the guide
173 | DVD Addin | File and Print | UnDiacritics Folder | — (no sample data needed) |  | Open the guide
174 | DVD Addin | File and Print | Resize Images | — (no sample data needed) |  | Open the guide
175 | DVD Addin | File and Print | Export Images | — (no sample data needed) |  | Open the guide
176 | DVD Addin | File and Print | Transcribe Audio | Transcribe Audio | Select the cell that will receive the transcript — ideally the top of an empty column, since each line goes into its own cell below. | Open the guide
177 | DVD Addin | File and Print | Unprotect Sheet | — (no sample data needed) |  | Open the guide
178 | DVD Addin | File and Print | Read PDF | — (no sample data needed) |  | Open the guide
179 | DVD Addin | File and Print | PDF Manager | — (no sample data needed) |  | Open the guide
180 | DVD Addin | File and Print | Stamp PDF | — (no sample data needed) |  | Open the guide
181 | DVD Addin | File and Print | Word → PDF | — (no sample data needed) |  | Open the guide
182 | DVD Addin | File and Print | Visio → PDF | — (no sample data needed) |  | Open the guide
183 | DVD Addin | File and Print | OCR file | OCR file | Select the cell that will receive the first line of the result . The text runs down the cells below in the same column, so keep that area empty. | Open the guide
184 | DVD Addin | File and Print | Extract Table | Extract Table | Select the cell that will be the top-left corner of the pasted table . | Open the guide
185 | DVD Addin | File and Print | OCR Screen Clip | OCR Screen Clip | Open the window holding the content you need (PDF, estimating software, drawing, web page…), switch back to Excel and select the cell that will receive the text . | Open the guide
186 | DVD Addin | File and Print | Batch print | Batch print | Build the form so that it is driven by one control cell — here B3 holds the element number and the cells below use VLOOKUP on B3. Add a cell listing the sheets to print, separated by + , and a cell building the PDF file name for each loop, e.g. ="BBNT_Cot_"&B3 . | Open the guide
187 | DVD Addin | File and Print | Set page margins | Set page margins | Select the sheets to set up: click the first sheet tab , then hold Shift and click the last one for a run of tabs (or hold Ctrl for individual tabs) — here the four record sheets BB-01 … BB-04. | Open the guide
188 | DVD Addin | File and Print | Sync page setup | — (no sample data needed) |  | Open the guide
189 | DVD Addin | File and Print | Print pages | — (no sample data needed) |  | Open the guide
190 | DVD Addin | File and Print | Mirror margins | — (no sample data needed) |  | Open the guide
191 | DVD Addin | File and Print | Sheets → PDF | Sheets → PDF | Save the workbook first (the PDFs go into the workbook's folder). Select the sheets to export: click the first tab , then hold Ctrl and click , (or Shift for a run of tabs) — leave the internal calculation sheets unselected. | Open the guide
192 | DVD Addin | File and Print | Send Email | Send Email | Prepare a data sheet with one row per e-mail (the Email Template gives you the layout). Cell B3 is the driver cell ; row 3 uses VLOOKUP on B3 to return the sender, To, Cc, Bcc, subject… of the matching row — the fields of the Send Email window point at this row. | Open the guide
193 | DVD Addin | File and Print | Import Email | — (no sample data needed) |  | Open the guide
194 | DVD Addin | File and Print | Email Template | Email Template | The template SendEmail.xlsx (from the add-in's Template folder) opens. Row 9 is the fixed header row : No., Send Date, Sender Email, To, Cc, Bcc, Subject, Name, Company, Body, Link, Attachment, Note — one e-mail per row from row 10; replace the sample rows with your own data . Cell B8 is the driver; row 8 pulls the row whose No. equals B8 . | Open the guide
195 | DVD Addin | File and Print | Merge to Word | Merge to Word | Prepare the data range with column headers in the first row — each header is the placeholder name used in the Word template, e.g. template BBNT_Cong.docx contains Today, [NgayNghiemThu], at chainage [LyTrinh]…. Every row below produces one Word file. | Open the guide
196 | DVD Addin | File and Print | Create Title | Create Title | The DVD Addin — Create title row box asks you to Select Title row to wrap with [...]: drag over the header row A3:F3 and click OK (Cancel leaves everything unchanged). | Open the guide
197 | DVD Addin | View and Sheets | Reading Layout | Reading Layout | Select any cell, for example the Amount on row 8: its whole row and column are covered by a translucent tint (by default cyan at 50%, row and column), leaving the selected cell itself clear. Move the selection with the mouse or arrow keys and the highlight follows. | Open the guide
198 | DVD Addin | View and Sheets | Sheet List | Sheet List | Open the workbook to index. The link back to the index is written into the same cell on every visible sheet — cell A1 by default — so keep that cell empty. | Open the guide
199 | DVD Addin | View and Sheets | Rename Sheets | Rename Sheets | On any sheet, build a table of two adjacent columns: the current sheet name on the left and the new name on the right . | Open the guide
200 | DVD Addin | View and Sheets | Sheet Numbering | Sheet Numbering | ⚠ This command acts on EVERY sheet of the workbook: Ctrl-select the sheets Sheet Numbering, right-click → Move or Copy → (new book), tick Create a copy, and try it in the new workbook. Drag the tabs into the reading/printing order you want. Hide any working sheet that should not be numbered — hidden sheets are skipped and take no number. | Open the guide
201 | DVD Addin | View and Sheets | UnDiacritics | UnDiacritics, Khối lượng móng, Đài móng - Cọc, Nghiệm thu thép, Phụ lục 01 | ⚠ This command acts on EVERY sheet of the workbook: Ctrl-select the sheets UnDiacritics, Khối lượng móng, Đài móng - Cọc, Nghiệm thu thép, Phụ lục 01, right-click → Move or Copy → (new book), tick Create a copy, and try it in the new workbook. Open the workbook whose sheet names contain Vietnamese accents. The command processes every sheet of the active workbook, hidden ones included. Cell D4 refers to the Khối lượng móng sheet. | Open the guide
202 | DVD Addin | View and Sheets | Hide Unselected | Hide Unselected, KL-Mong, KL-Than, DonGia-NoiBo, Chietinh, Phuluc, Nhap1 | ⚠ This command acts on EVERY sheet of the workbook: Ctrl-select the sheets Hide Unselected, KL-Mong, KL-Than, DonGia-NoiBo, Chietinh, Phuluc, Nhap1, right-click → Move or Copy → (new book), tick Create a copy, and try it in the new workbook. In the tab bar, select the sheets you want to keep: click Tonghop , then Ctrl-click KL-Mong , KL-Than and Phuluc (Shift-click takes a contiguous run). Here DonGia-NoiBo, Chietinh and Nhap1 are internal figures that must not leave the office. | Open the guide
203 | DVD Addin | View and Sheets | Unhide All | Unhide All, Chietinh-VT, Giavatlieu, DonGia-CT, KL, Phuluc (2) | ⚠ This command acts on EVERY sheet of the workbook: Ctrl-select the sheets Unhide All, Chietinh-VT, Giavatlieu, DonGia-CT, KL, Phuluc (2), right-click → Move or Copy → (new book), tick Create a copy, and try it in the new workbook. Open the workbook to unhide. Here an estimate received from the consultant shows only 3 sheets, yet the unit rate refers to a Chietinh-VT sheet that is not in the tab bar — a sure sign of hidden sheets. | Open the guide
204 | DVD Addin | View and Sheets | Navigation | — (no sample data needed) |  | Open the guide
205 | DVD Addin | View and Sheets | Tab Bar | — (no sample data needed) |  | Open the guide
206 | DVD Addin | View and Sheets | View Image | View Image | The add-in arms every picture on the sheet that has no macro of its own and reports the count in the status bar (in the picture, the grey cells stand for the photos). The mode is remembered: when you switch to another sheet or workbook, its pictures are armed automatically. | Open the guide
207 | DVD Addin | View and Sheets | Hide Empty Rows | Hide Empty Rows | Excel's range picker appears (Select data range). Drag-select the range to check, covering exactly the columns that hold data — here the printed form has 10 rows but only 5 are used, rows 9–13 are blank — then click OK. Hold Ctrl to add separate areas. | Open the guide
208 | DVD Addin | View and Sheets | Reset Note | — (no sample data needed) |  | Open the guide
209 | DVD Addin | AI | AI Chat | — (no sample data needed) |  | Open the guide
210 | DVD Addin | AI | Explain formula (Coach) | Explain formula (Coach), Pour log | Select the cell whose formula you want explained — here a SUMPRODUCT over named ranges . | Open the guide
211 | DVD Addin | AI | Fix formula error | Fix formula error, DonGia | Select one cell that shows an error — here a VLOOKUP returning #N/A . | Open the guide
212 | DVD Addin | AI | Grammar | Grammar | Select the cells whose text needs spelling and grammar fixes — numbers, blanks and formula cells are skipped. | Open the guide
213 | DVD Addin | AI | Solver | Solver | Select the cell that will receive the answers — the command writes to the active cell. | Open the guide
214 | DVD Addin | AI | DVD Chat | DVD Chat | To discuss exact figures: select the range on the sheet , click the 📋 button (attach the selected Excel cell / range) in the chat pane, write your message and send — the message carries the reference and the data of that range. | Open the guide
215 | DVD Addin | About | Lang: EN | — (no sample data needed) |  | Open the guide
216 | DVD Addin | About | Preferences | — (no sample data needed) |  | Open the guide
217 | DVD Addin | About | Quick start guide | — (no sample data needed) |  | Open the guide
218 | DVD Addin | About | User guide | — (no sample data needed) |  | Open the guide
219 | DVD Addin | About | Restore data | — (no sample data needed) |  | Open the guide
220 | DVD Addin | About | Check Update | — (no sample data needed) |  | Open the guide
221 | DVD Addin | About | Download Tool | — (no sample data needed) |  | Open the guide
222 | DVD Addin | About | Export support log | — (no sample data needed) |  | Open the guide
223 | DVD Addin | About | About | — (no sample data needed) |  | Open the guide
224 | DVD Addin | About | License | — (no sample data needed) |  | Open the guide

## Gantt Chart
FOUNDATION WORKS SCHEDULE – 9-STOREY OFFICE BUILDING |  |  |  |  | ← Index
Activity ID | Activity Name | Duration | Start | Finish
A1010 | Excavate foundation pits | 6 | 2026-10-05 | 2026-10-10
A1020 | Blinding concrete | 2 | 2026-10-12 | 2026-10-13
A1030 | Pile cap rebar and formwork | 8 | 2026-10-14 | 2026-10-22
A1040 | Pile caps, ground beams | 2 | 2026-10-23 | 2026-10-24
A1050 | Backfill, raise ground floor | 6 | 2026-10-26 | 2026-10-31
A1060 | Foundation acceptance | 0 |  | 2026-11-02

## Auto Calc
Activity ID | Activity Name | Duration | Start | Finish | Predecessors | ← Index
A1010 | Excavate foundation pits | 4 | 2026-10-05 | 2026-10-10
A1020 | Blinding concrete | 2 | 2026-10-12 | 2026-10-13 | A1010FS
A1030 | Pile cap rebar and formwork | 8 | 2026-10-14 | 2026-10-22 | A1020FS
A1040 | Pile caps, ground beams | 2 | 2026-10-23 | 2026-10-24 | A1030FS
A1050 | Backfill, raise ground floor | 6 | 2026-10-26 | 2026-10-31 | A1040FS
A1060 | Foundation acceptance | 0 |  | 2026-11-02 | A1050FS

## Auto Draw
FOUNDATION WORKS SCHEDULE – 9-STOREY OFFICE BUILDING | [11 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | October 2026 |  |  |  |  | November 2026
[5 empty] | W40 | W41 | W42 | W43 | W44 | W45 | W46
A1010 | Excavate foundation pits | 8 | 2026-10-05 | 2026-10-10 |  | ▀▀▀▀
A1020 | Blinding concrete | 2 | 2026-10-12 | 2026-10-13 |  |  | ▀
A1030 | Pile cap rebar and formwork | 8 | 2026-10-14 | 2026-10-22 |  |  | ▀▀▀▀▀▀
A1040 | Pile caps, ground beams | 2 | 2026-10-23 | 2026-10-24 |  |  |  | ▀
A1050 | Backfill, raise ground floor | 6 | 2026-10-26 | 2026-10-31 |  |  |  |  | ▀▀▀▀
A1060 | Foundation acceptance | 0 |  | 2026-11-02 | [5 empty] | ◆

## Update schedule (data date)
Activity ID | Activity Name | Duration | Start | Finish | Actual Start | Actual Finish | Complete (%) | ← Index
A1010 | Excavate foundation pits | 6 | 2026-10-05 | 2026-10-10 | 2026-10-05 | 2026-10-10 | 100%
A1020 | Blinding concrete | 2 | 2026-10-12 | 2026-10-14 | 2026-10-12 | 2026-10-14 | 100%
A1030 | Pile cap rebar and formwork | 8 | 2026-10-15 | 2026-10-23 | 2026-10-15 |  | 25%
A1035 | Prefabricate column starter bars | 3 | 2026-10-15 | 2026-10-17 |  |  | 0%
A1040 | Pile caps, ground beams | 2 | 2026-10-24 | 2026-10-26 |  |  | 0%
A1050 | Backfill, raise ground floor | 6 | 2026-10-27 | 2026-11-02 |  |  | 0%
A1060 | Foundation acceptance | 0 |  | 2026-11-03 |  |  | 0%

## Update Status
Activity Name | Duration | Start | Finish | Complete (%) | Actual Start | Actual Finish | BAC | EV | ← Index
Columns L2 | 4 | 05/10 | 08/10 | 100% | 05/10 | 08/10 | 120 | 120
Slab rebar L2 | 8 | 09/10 | 17/10 | 100% | 09/10 | 19/10 | 260 | 260
Brickwork L1 | 10 | 12/10 | 23/10 | 60% | 13/10 |  | 150 | 90
Columns L3 | 3 | 19/10 | 21/10 | 50% | 20/10 |  | 90 | 45
Conduits L1 | 5 | 16/10 | 21/10 | 0% |  |  | 70 | 0
Plaster L1 | 8 | 26/10 | 03/11 | 0% |  |  | 180 | 0

## Constraints
Activity ID | Activity Name | Duration | Start | Finish | Predecessors | ← Index
A1010 | Excavate foundation pits | 6 | 2026-10-05 | 2026-10-10
A1020 | Blinding concrete | 2 | 2026-10-12 | 2026-10-13 | A1010FS
A1030 | Pile cap rebar and formwork | 8 | 2026-10-14 | 2026-10-22 | A1020FS
A1040 | Pile caps, ground beams | 2 | 2026-10-23 | 2026-10-24 | A1030FS
A1050 | Backfill, raise ground floor | 6 | 2026-10-26 | 2026-10-31 | A1040FS
A1070 | Erect tower crane | 3 | 2026-10-26 | 2026-10-28 | A1040FS

## Header Language
SCHEDULE — 9-storey office building | [6 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | Predecessors | Complete (%)
A1010 | Excavate foundation pits | 6 | 2026-10-05 | 2026-10-10 |  | 100%
A1020 | Blinding concrete | 2 | 2026-10-12 | 2026-10-13 | A1010FS | 100%
A1030 | Pile cap rebar and formwork | 8 | 2026-10-14 | 2026-10-22 | A1020FS | 40%
A1040 | Pile caps, ground beams | 2 | 2026-10-23 | 2026-10-24 | A1030FS | 0%
A1050 | Backfill, raise ground floor | 6 | 2026-10-26 | 2026-10-31 | A1040FS | 0%

## Export XML (P6-MSP)
Activity ID | Activity Name | Duration | Start | Finish | Predecessors | ← Index
A1010 | Excavate foundation pits | 6 | 2026-10-05 | 2026-10-10
A1020 | Blinding concrete | 2 | 2026-10-12 | 2026-10-13 | A1010FS
A1030 | Pile cap rebar and formwork | 8 | 2026-10-14 | 2026-10-22 | A1020FS
A1040 | Pile caps, ground beams | 2 | 2026-10-23 | 2026-10-24 | A1030FS
A1050 | Backfill, raise ground floor | 6 | 2026-10-26 | 2026-10-31 | A1040FS
A1060 | Foundation acceptance | 0 |  | 2026-11-02 | A1050FS

## AI Gantt Builder
BILL OF QUANTITIES – 9-STOREY OFFICE BUILDING |  |  |  | ← Index
Code | Item name | Unit | Quantity
AB.25112 | Machine excavation of foundations, soil grade II | 100m³ | 12.5
AF.11111 | Blinding concrete 4x6 aggregate, M100 | m³ | 38.4
AF.61120 | Foundation rebar, diameter ≤18 mm | t | 24.6
AF.81122 | Foundation formwork | 100m² | 3.85
AF.21225 | Foundation concrete 1x2 aggregate, M300 | m³ | 286.5
AB.13112 | Backfill to K95 compaction | m³ | 420
AF.22245 | Column concrete 1x2 aggregate, M350 | m³ | 42.8
AF.22345 | Beam and slab concrete 1x2 aggregate, M300 | m³ | 156.2

## Schedule Recovery
CONSTRUCTION SCHEDULE — 9-STOREY OFFICE BUILDING | [5 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | Complete (%)
A1010 | Concrete, level-3 columns | 6 | 2026-09-07 | 2026-09-12 | 100%
A1020 | Formwork & rebar, level-3 slab | 15 | 2026-09-14 | 2026-09-30 | 75%
A1030 | Concrete, level-3 slab | 2 | 2026-10-01 | 2026-10-02 | 0%
A1040 | Column rebar & forms, level 4 | 6 | 2026-10-05 | 2026-10-10 | 0%
A2010 | Blockwork, level 1 | 18 | 2026-09-14 | 2026-10-03 | 55%
A2020 | Blockwork, level 2 | 12 | 2026-10-05 | 2026-10-17 | 0%
A3010 | Plumbing pipework, level 1 | 11 | 2026-09-21 | 2026-10-02 | 30%
A3020 | Concealed wiring, level 1 | 6 | 2026-09-28 | 2026-10-03 | 10%

## Health Check
CONSTRUCTION SCHEDULE — 9-STOREY OFFICE BUILDING | [9 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | Predecessors | Actual Start | Actual Finish | Complete (%) | Total Float
A1010 | Concrete, level-3 columns | 6 | 2026-09-07 | 2026-09-12 |  | 2026-09-07 | 2026-09-12 | 100% | 0
A1020 | Formwork & rebar, level-3 slab | 15 | 2026-09-14 | 2026-09-30 | A1010 | 2026-09-14 |  | 75% | 6
A1030 | Concrete, level-3 slab | 2 | 2026-10-01 | 2026-10-02 | A1020 |  |  | 0% | 6
A1040 | Column rebar & forms, level 4 | 6 | 2026-10-05 | 2026-10-10 | A1030FS+2 |  |  | 0% | 6
A2010 | Blockwork, level 1 | 18 | 2026-09-14 | 2026-10-03 | A1010 | 2026-09-14 |  | 55% | 0
A2020 | Blockwork, level 2 | 12 | 2026-10-05 | 2026-10-17 | A2010 |  |  | 0% | 0
A3010 | Plumbing pipework, level 1 | 11 | 2026-09-21 | 2026-10-02 | A2010SS+6 | 2026-09-21 |  | 30% | 12
A3020 | Concealed wiring, level 1 | 6 | 2026-09-28 | 2026-10-03 | A3010SS+6 | 2026-09-28 |  | 10% | 12

## EVM Report
CONSTRUCTION SCHEDULE — 9-STOREY OFFICE BUILDING | [7 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | Complete (%) | BAC | AC
A1010 | Concrete, level-3 columns | 6 | 2026-09-07 | 2026-09-12 | 100% | 420000000 | 436000000
A1020 | Formwork & rebar, level-3 slab | 15 | 2026-09-14 | 2026-09-30 | 75% | 1250000000 | 1010000000
A1030 | Concrete, level-3 slab | 2 | 2026-10-01 | 2026-10-02 | 0% | 980000000
A1040 | Column rebar & forms, level 4 | 6 | 2026-10-05 | 2026-10-10 | 0% | 510000000
A2010 | Blockwork, level 1 | 18 | 2026-09-14 | 2026-10-03 | 55% | 640000000 | 372000000
A2020 | Blockwork, level 2 | 12 | 2026-10-05 | 2026-10-17 | 0% | 610000000
A3010 | Plumbing pipework, level 1 | 11 | 2026-09-21 | 2026-10-02 | 30% | 360000000 | 126000000
A3020 | Concealed wiring, level 1 | 6 | 2026-09-28 | 2026-10-03 | 10% | 240000000 | 30000000

## Variance Dashboard
CONSTRUCTION SCHEDULE — 9-STOREY OFFICE BUILDING | [9 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | Actual Start | Actual Finish | Complete (%) | BAC | AC
A1010 | Concrete, level-3 columns | 6 | 2026-09-07 | 2026-09-12 | 2026-09-07 | 2026-09-12 | 100% | 420000000 | 436000000
A1020 | Formwork & rebar, level-3 slab | 15 | 2026-09-14 | 2026-09-30 | 2026-09-14 |  | 75% | 1250000000 | 1010000000
A1030 | Concrete, level-3 slab | 2 | 2026-10-01 | 2026-10-02 |  |  | 0% | 980000000
A1040 | Column rebar & forms, level 4 | 6 | 2026-10-05 | 2026-10-10 |  |  | 0% | 510000000
A2010 | Blockwork, level 1 | 18 | 2026-09-14 | 2026-10-03 | 2026-09-14 |  | 55% | 640000000 | 372000000
A2020 | Blockwork, level 2 | 12 | 2026-10-05 | 2026-10-17 |  |  | 0% | 610000000
A3010 | Plumbing pipework, level 1 | 11 | 2026-09-21 | 2026-10-02 | 2026-09-21 |  | 30% | 360000000 | 126000000
A3020 | Concealed wiring, level 1 | 6 | 2026-09-28 | 2026-10-03 | 2026-09-28 |  | 10% | 240000000 | 30000000

## 2-Week Lookahead
CONSTRUCTION SCHEDULE — 9-STOREY OFFICE BUILDING | [7 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | Actual Start | Actual Finish | Complete (%)
A1010 | Concrete, level-3 columns | 6 | 2026-09-07 | 2026-09-12 | 2026-09-07 | 2026-09-12 | 100%
A1020 | Formwork & rebar, level-3 slab | 15 | 2026-09-14 | 2026-09-30 | 2026-09-14 |  | 75%
A1030 | Concrete, level-3 slab | 2 | 2026-10-01 | 2026-10-02 |  |  | 0%
A1040 | Column rebar & forms, level 4 | 6 | 2026-10-05 | 2026-10-10 |  |  | 0%
A2010 | Blockwork, level 1 | 18 | 2026-09-14 | 2026-10-03 | 2026-09-14 |  | 55%
A2020 | Blockwork, level 2 | 12 | 2026-10-05 | 2026-10-17 |  |  | 0%
A3005 | M&E sleeves, level-2 slab | 8 | 2026-09-10 | 2026-09-18 | 2026-09-10 |  | 80%
A3010 | Plumbing pipework, level 1 | 11 | 2026-09-21 | 2026-10-02 | 2026-09-21 |  | 30%
A3020 | Concealed wiring, level 1 | 6 | 2026-09-28 | 2026-10-03 | 2026-09-28 |  | 10%

## 3-Week Lookahead
CONSTRUCTION SCHEDULE — 9-STOREY OFFICE BUILDING | [7 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | Actual Start | Actual Finish | Complete (%)
A1010 | Concrete, level-3 columns | 6 | 2026-09-07 | 2026-09-12 | 2026-09-07 | 2026-09-12 | 100%
A1020 | Formwork & rebar, level-3 slab | 15 | 2026-09-14 | 2026-09-30 | 2026-09-14 |  | 75%
A1030 | Concrete, level-3 slab | 2 | 2026-10-01 | 2026-10-02 |  |  | 0%
A1040 | Column rebar & forms, level 4 | 6 | 2026-10-05 | 2026-10-10 |  |  | 0%
A2010 | Blockwork, level 1 | 18 | 2026-09-14 | 2026-10-03 | 2026-09-14 |  | 55%
A2020 | Blockwork, level 2 | 12 | 2026-10-05 | 2026-10-17 |  |  | 0%
A3005 | M&E sleeves, level-2 slab | 8 | 2026-09-10 | 2026-09-18 | 2026-09-10 |  | 80%
A3010 | Plumbing pipework, level 1 | 11 | 2026-09-21 | 2026-10-02 | 2026-09-21 |  | 30%
A3020 | Concealed wiring, level 1 | 6 | 2026-09-28 | 2026-10-03 | 2026-09-28 |  | 10%

## Schedule (custom range)
CONSTRUCTION SCHEDULE — 9-STOREY OFFICE BUILDING | [5 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | Predecessors
A1010 | Concrete, level-3 columns | 6 | 2026-09-07 | 2026-09-12
A1020 | Formwork & rebar, level-3 slab | 15 | 2026-09-14 | 2026-09-30 | A1010
A1030 | Concrete, level-3 slab | 2 | 2026-10-01 | 2026-10-02 | A1020
A1040 | Column rebar & forms, level 4 | 6 | 2026-10-05 | 2026-10-10 | A1030FS+2
A2010 | Blockwork, level 1 | 18 | 2026-09-14 | 2026-10-03 | A1010
A2020 | Blockwork, level 2 | 12 | 2026-10-05 | 2026-10-17 | A2010
A3010 | Plumbing pipework, level 1 | 11 | 2026-09-21 | 2026-10-02 | A2010SS+6
A3020 | Concealed wiring, level 1 | 6 | 2026-09-28 | 2026-10-03 | A3010SS+6

## Snapshot
CONSTRUCTION SCHEDULE — 9-STOREY OFFICE BUILDING | [7 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | Complete (%) | BAC | AC
A1010 | Concrete, level-3 columns | 6 | 2026-09-07 | 2026-09-12 | 100% | 420000000 | 436000000
A1020 | Formwork & rebar, level-3 slab | 15 | 2026-09-14 | 2026-09-30 | 75% | 1250000000 | 1010000000
A1030 | Concrete, level-3 slab | 2 | 2026-10-01 | 2026-10-02 | 0% | 980000000
A1040 | Column rebar & forms, level 4 | 6 | 2026-10-05 | 2026-10-10 | 0% | 510000000
A2010 | Blockwork, level 1 | 18 | 2026-09-14 | 2026-10-03 | 55% | 640000000 | 372000000
A2020 | Blockwork, level 2 | 12 | 2026-10-05 | 2026-10-17 | 0% | 610000000
A3010 | Plumbing pipework, level 1 | 11 | 2026-09-21 | 2026-10-02 | 30% | 360000000 | 126000000
A3020 | Concealed wiring, level 1 | 6 | 2026-09-28 | 2026-10-03 | 10% | 240000000 | 30000000

## Manpower
CONSTRUCTION SCHEDULE — 9-STOREY OFFICE BUILDING | [5 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | Manpower
A1010 | Concrete, level-3 columns | 6 | 2026-09-07 | 2026-09-12 | 12
A1020 | Formwork & rebar, level-3 slab | 15 | 2026-09-14 | 2026-09-30 | 24
A1030 | Concrete, level-3 slab | 2 | 2026-10-01 | 2026-10-02 | 30
A1040 | Column rebar & forms, level 4 | 6 | 2026-10-05 | 2026-10-10 | 14
A2010 | Blockwork, level 1 | 18 | 2026-09-14 | 2026-10-03 | 10
A2020 | Blockwork, level 2 | 12 | 2026-10-05 | 2026-10-17 | 10
A3010 | Plumbing pipework, level 1 | 11 | 2026-09-21 | 2026-10-02 | 4
A3020 | Concealed wiring, level 1 | 6 | 2026-09-28 | 2026-10-03 | 4

## Level resources
CONSTRUCTION SCHEDULE — 9-STOREY OFFICE BUILDING | [6 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | Predecessors | Manpower
A1010 | Concrete, level-3 columns | 6 | 2026-09-07 | 2026-09-12 |  | 12
A1020 | Formwork & rebar, level-3 slab | 15 | 2026-09-14 | 2026-09-30 | A1010 | 24
A1030 | Concrete, level-3 slab | 2 | 2026-10-01 | 2026-10-02 | A1020 | 30
A1040 | Column rebar & forms, level 4 | 6 | 2026-10-05 | 2026-10-10 | A1030FS+2 | 14
A2010 | Blockwork, level 1 | 18 | 2026-09-14 | 2026-10-03 | A1010 | 10
A2020 | Blockwork, level 2 | 12 | 2026-10-05 | 2026-10-17 | A2010 | 10
A3010 | Plumbing pipework, level 1 | 11 | 2026-09-21 | 2026-10-02 | A2010SS+6 | 4
A3020 | Concealed wiring, level 1 | 6 | 2026-09-28 | 2026-10-03 | A3010SS+6 | 4

## Cash-flow
CONSTRUCTION SCHEDULE — 9-STOREY OFFICE BUILDING | [5 empty] | ← Index
Activity ID | Activity Name | Duration | Start | Finish | BAC
A1010 | Concrete, level-3 columns | 6 | 2026-09-07 | 2026-09-12 | 420000000
A1020 | Formwork & rebar, level-3 slab | 15 | 2026-09-14 | 2026-09-30 | 1250000000
A1030 | Concrete, level-3 slab | 2 | 2026-10-01 | 2026-10-02 | 980000000
A1040 | Column rebar & forms, level 4 | 6 | 2026-10-05 | 2026-10-10 | 510000000
A2010 | Blockwork, level 1 | 18 | 2026-09-14 | 2026-10-03 | 640000000
A2020 | Blockwork, level 2 | 12 | 2026-10-05 | 2026-10-17 | 610000000
A3010 | Plumbing pipework, level 1 | 11 | 2026-09-21 | 2026-10-02 | 360000000
A3020 | Concealed wiring, level 1 | 6 | 2026-09-28 | 2026-10-03 | 240000000

## Rebar Cut
Ø (mm) | Length (mm) | Quantity | Marks | ← Index
8 | 1320 | 240 | 3
12 | 2080 | 120 | 4
20 | 5700 | 24 | 1
20 | 3880 | 12 | 2

## Bar schedule
Mark | Member | Ø (mm) | Shape | A | B | C | Members | Bars/member | ← Index
1 | Beam D1 | 20 | 00 | 5700 |  |  | 6 | 4
2 | Beam D1 | 20 | 21 | 3500 | 400 |  | 6 | 2
3 | Beam D1 | 8 | 51 | 200 | 400 |  | 6 | 40
4 | Slab S5 | 12 | 31 | 150 | 1800 | 150 | 1 | 120

## Bar Cut 1D
Length | Qty | Material | Label | Priority | ← Index
2350 | 40 | HOP50 | Cross bracing | 0
1800 | 24 | HOP50 | Uprights | 0
950 | 30 | HOP50 | Diagonals | 0

## Bar Cut 1D · CatThanh_Thanh
Length | Qty (0=∞) | Material | Kerf | Trim | Cost | Priority | Min offcut | ← Index
6000 | 0 | HOP50 | 3 | 10 | 148000 | 0 | 1000

## Panel Cut 2D
Length | Width | Qty | Material | Rotate (1/0) | Label | Priority | Band (T B L R) | Grind (T B L R) | ← Index
1200 | 600 | 18 | PLY18 | 1 | Column C1 form | 0
900 | 450 | 24 | PLY18 | 1 | Beam D2 form | 0
2000 | 300 | 10 | PLY18 | 0 | Edge board | 0

## Panel Cut 2D · CatTam_Tam
Length | Width | Qty (0=∞) | Material | Kerf | Trim | Cost | Priority | Min offcut | Band thickness | ← Index
2440 | 1220 | 0 | PLY18 | 4 | 5 | 520000 | 0 | 300

## Cutting Tpl
Ø (mm) | Chiều dài (mm) | Số lượng | Ký hiệu | ◀ DỮ LIỆU VÍ DỤ | ← Index
25 | 8300 | 256 | 1 | 12 dòng tô màu bên trái là ví dụ — xoá hết rồi nhập số liệu của bạn. Bốn cột này đúng bằng thứ lệnh Thống kê thép → Xuất danh sách cắt ghi ra, nên dán thẳng từ đó sang cũng được.
25 | 7300 | 256 | 2
16 | 4620 | 10 | 3
16 | 3620 | 10 | 4
16 | 4830 | 1 | 5
16 | 11700 | 1 | 6
16 | 9790 | 1 | 7
16 | 8660 | 1 | 9
16 | 3700 | 1 | 10
16 | 6870 | 1 | 11
10 | 660 | 914 | 1a
8 | 1380 | 196 | 3a

## Bar Tpl
Length | Qty | Material | Label | Priority | ← Index
2100 | 4 | Hộp 50x50 | Cột | 0
1500 | 6 | Hộp 50x50 | Xà ngang | 0
1200 | 10 | Hộp 50x50 | Thanh giằng | 0
800 | 8 | Hộp 50x50 | Đố | 0

## Panel Tpl
Length | Width | Qty | Material | Rotate (1/0) | Label | Priority | Band (T B L R) | Grind (T B L R) | ← Index
1450 | 900 | 22 | KINH8 | 0 | Grid A | 0
1450 | 600 | 14 | KINH8 | 0 | Grid B | 0

## New Diary
WORK ITEMS – 9-STOREY OFFICE BUILDING | [5 empty] | ← Index
| Diary period from: | 2026-11-02 | to: | 2026-11-08
TT | Work description | Start | Finish | Accepted | Rest days
1 | Level 5 column reinforcement | 2026-11-02 | 2026-11-03 | 2026-11-04
2 | Level 5 column formwork | 2026-11-03 | 2026-11-04 | 2026-11-04
3 | Level 5 column concrete pour | 2026-11-05 | 2026-11-05 | 2026-11-06
4 | Level 6 beam & slab formwork | 2026-11-06 | 2026-11-08 | 2026-11-09
5 | Level 3 perimeter block wall | 2026-11-02 | 2026-11-08 | 2026-11-10 | 04/11/2026+06/11/2026

## Export Category
ACCEPTANCE RECORD LOG – 9-STOREY OFFICE BUILDING | [6 empty] | ← Index
STT | Code | Work item | Location | Accepted | Record no. | Note
A. SUBSTRUCTURE
1 | DD-01 | Excavation, footings F1–F6 | Grid 1–3 / A–C | 2026-10-09 | NTCV-001
2 | BTL-01 | Blinding concrete, F1–F6 | Grid 1–3 / A–C | 2026-10-11 | NTCV-002
3 | CT-01 | Footing reinforcement, F1–F6 | Grid 1–3 / A–C | 2026-10-15 | NTCV-003
4 | VK-01 | Footing formwork, F1–F6 | Grid 1–3 / A–C | 2026-10-16 | NTCV-004
5 | BT-01 | Footing concrete F1–F6 (B25) | Grid 1–3 / A–C | 2026-10-18 | NTCV-005 | 3 sample sets

## Pick Rest Days
WORK ITEMS – 9-STOREY OFFICE BUILDING | [5 empty] | ← Index
| Diary period from: | 2026-11-02 | to: | 2026-11-08
TT | Work description | Start | Finish | Accepted | Rest days
1 | Level 5 column reinforcement | 2026-11-02 | 2026-11-03 | 2026-11-04
2 | Level 5 column formwork | 2026-11-03 | 2026-11-04 | 2026-11-04
3 | Level 5 column concrete pour | 2026-11-05 | 2026-11-05 | 2026-11-06
4 | Level 6 beam & slab formwork | 2026-11-06 | 2026-11-08 | 2026-11-09
5 | Level 3 perimeter block wall | 2026-11-02 | 2026-11-08 | 2026-11-10

## Work Record Tpl
Mucluc |  |  | ← Index
THÔNG TIN CHUNG
| Dự án | Đầu tư xây dựng Nhà văn phòng 9 tầng
| Công trình | Nhà văn phòng 9 tầng
| Địa điểm | Phường Dịch Vọng, Quận Cầu Giấy, TP Hà Nội
| Tỉnh thành | Hà Nội
| Hợp đồng | 15/2026/HĐTC-XL02
| Ngày ký hợp đồng | 2026-06-15
Phụ lục hợp đồng
Ngày ký PLHĐ
| Gói thầu | XL-02: Thi công xây dựng phần thân
| Chủ đầu tư | Công ty CP Đầu tư PQR
| Tư vấn thiết kế | Công ty CP Tư vấn Thiết kế MNO
| Tư vấn giám sát | Công ty Tư vấn ABC
| Nhà thầu thi công | Công ty Xây dựng XYZ
| Giấy phép xây dựng | 125/GPXD

## Material Record Tpl
Mucluc |  |  | ← Index
THÔNG TIN CHUNG
| Dự án | Đầu tư xây dựng Nhà văn phòng 9 tầng
| Công trình | Nhà văn phòng 9 tầng
| Địa điểm | Phường Dịch Vọng, Quận Cầu Giấy, TP Hà Nội
| Tỉnh thành | Hà Nội
| Hợp đồng | 15/2026/HĐTC-XL02
| Ngày ký hợp đồng | 2026-06-15
Phụ lục hợp đồng
Ngày ký PLHĐ
| Gói thầu | XL-02: Thi công xây dựng phần thân
| Chủ đầu tư | Công ty CP Đầu tư PQR
| Tư vấn thiết kế | Công ty CP Tư vấn Thiết kế MNO
| Tư vấn giám sát | Công ty Tư vấn ABC
| Nhà thầu thi công | Công ty Xây dựng XYZ
| Giấy phép xây dựng | 125/GPXD

## Diary Template
NHẬT KÝ CÔNG TRÌNH | [5 empty] | ← Index
Tỉnh/TP, ngày 05 tháng 11 năm 2026
I. Điều kiện thời tiết: | Nắng |  |  | Nhiệt độ TB: | 28
II. Nhân lực, máy móc thiết bị:
Nhân lực |  | Số lượng | Máy móc thiết bị |  | Số lượng
Chỉ huy công trường |  | 1 | Máy ép cọc
Kỹ sư |  | 4 | Xe đào |  | 1
Cán bộ ATLĐ&VSMT |  | 1 | Xe ủi
Thủ kho |  | 1 | Xe lu
Bảo vệ |  | 2 | Máy trộn |  | 1
Công nhân |  | 45 | Máy trắc đạc |  | 1
|  |  | Máy laser |  | 1
III. Nội dung công việc thực hiện trong ngày :
1. Vật tư, vật liệu ra vào công trường:

## DATA
← Index
Date line | Tỉnh/TP, ngày 05 tháng 11 năm 2026

## Test Plan
FOUNDATION MATERIAL QUANTITIES |  |  |  | ← Index
TT | Item | Unit | Quantity
1 | Bê tông thương phẩm M300 | m³ | 286.5
2 | Thép CB400-V | t | 34.2
3 | Xi măng PCB40 | t | 18
4 | Cát vàng xây trát | m³ | 42
5 | Gạch rỗng 2 lỗ tuynel | pcs | 12500

## Acceptance Plan
SUBSTRUCTURE SCHEDULE – 9-STOREY OFFICE BUILDING |  |  |  |  | ← Index
Activity ID | Task Name | Start | Finish | Days
1.1 | Excavation of footings | 2026-10-05 | 2026-10-09 | 5
1.2 | Blinding concrete, footings F1–F6 | 2026-10-10 | 2026-10-11 | 2
1.3 | Footing reinforcement F1–F6 | 2026-10-12 | 2026-10-15 | 4
1.4 | Footing formwork F1–F6 | 2026-10-14 | 2026-10-16 | 3
1.5 | Footing concrete pour F1–F6 | 2026-10-17 | 2026-10-17 | 1
1.6 | Backfilling of footings | 2026-10-20 | 2026-10-22 | 3

## Acceptance Record
CONSTRUCTION WORK ACCEPTANCE PLAN | [9 empty] | ← Index
Project: 9-storey office building – Package XL-02 Date: 08/10/2026 Source: schedule 'Schedule'
No. | Code | Work item / acceptance scope | Acceptance type | Applicable standard | Start date | Planned acceptance | Inspection parties | Status | Note
1 | 1.1 | Excavation of footings | Construction work | TCVN 4447:2012 | 2026-10-05 | 2026-10-09 | Client/Supervision consultant; Contractor's technical staff | Pending
2 | 1.2 | Blinding concrete, footings F1–F6 | Construction work | TCVN 4453:1995 | 2026-10-10 | 2026-10-11 | Client/Supervision consultant; Contractor's technical staff | Pending
3 | 1.3 | Footing reinforcement F1–F6 | Construction work | TCVN 4453:1995; TCVN 1651-2:2018 | 2026-10-12 | 2026-10-15 | Client/Supervision consultant; Contractor's technical staff | Pending
4 | 1.4 | Footing formwork F1–F6 | Construction work | TCVN 4453:1995 | 2026-10-14 | 2026-10-16 | Client/Supervision consultant; Contractor's technical staff | Pending
5 | 1.5 | Footing concrete pour F1–F6 | Construction work | TCVN 4453:1995 | 2026-10-17 | 2026-10-17 | Client/Supervision consultant; Contractor's technical staff | Pending
6 | 1.6 | Backfilling of footings | Construction work | TCVN 4447:2012 | 2026-10-20 | 2026-10-22 | Client/Supervision consultant; Contractor's technical staff | Pending

## AI Construction Estimate
FOUNDATION BILL OF QUANTITIES — 9-STOREY OFFICE BUILDING | [6 empty] | ← Index
No. | Item | Unit | Quantity | Unit price | Price source | Note
1 | Bê tông lót móng M100 đá 4x6 | m3 | 18.6
2 | Bê tông móng M250 đá 1x2 | m3 | 142.5
3 | Ván khuôn móng | m2 | 236
4 | Cốt thép móng D≤10 | kg | 2850
5 | Xi măng PCB40 | t | 12.5

## Interim Payment
CONTRACT BILL OF QUANTITIES — 9-STOREY OFFICE BUILDING | [7 empty] | ← Index
No. | Item | Code | Unit | Contract qty | Unit price | Amount | % done (cum.)
1 | Excavation of foundation pits | AB.25113 | m3 | 1250 | 85000 | 106250000 | 100%
2 | Foundation concrete M300 | AF.22230 | m3 | 286.5 | 1850000 | 530025000 | 100%
3 | Foundation reinforcement | AF.61130 | t | 34.2 | 21500000 | 735300000 | 100%
4 | Column concrete L1–3 M300 | AF.22250 | m3 | 96 | 2050000 | 196800000 | 40%

## Compare BoQ
FOUNDATION BILL OF QUANTITIES — MEASURED | [5 empty] | ← Index
No. | Code | Description | Unit | Quantity | Unit price
1 | AB.25113 | Machine excavation, soil class III | m3 | 1312.5 | 85000
2 | AF.11213 | Blinding concrete M100 | m3 | 18.6 | 1320000
3 | AF.22230 | Foundation concrete M300 | m3 | 279.8 | 1850000
4 | AF.61130 | Foundation rebar dia. ≤18 mm | t | 36.05 | 21500000
5 | AK.95121 | Waterproof coating, lift pit | m2 | 48 | 125000

## Price adjustment
MATERIALS ELIGIBLE FOR PRICE ADJUSTMENT — Q3/2026 | [5 empty] | ← Index
No. | Material | Unit | Quantity | Base price (contract) | New price (adjustment date)
1 | Rebar CB300-V D10 | kg | 18500 | 15200 | 16850
2 | Rebar CB400-V D16–D25 | kg | 26400 | 15050 | 16400
3 | Cement PCB40 | t | 145 | 1550000 | 1680000
4 | Concrete sand | m3 | 210 | 380000 | 420000

## Estimate bridge
DETAILED COST ESTIMATE | [8 empty] | ← Index
Project: 9-storey office building
Section: Foundations
No. | Code | Work description | Unit | Quantity | Material rate | Labour rate | Plant rate | Amount
A |  | FOUNDATIONS
1 | AB.25113 | Machine excavation ≤1.25 m3 bucket, soil class III | m3 | 1250 | 0 | 9850 | 22400 | 40312500
2 | AF.11213 | Blinding concrete 4x6 aggregate M100 | m3 | 18.6 | 985000 | 245000 | 32000 | 23473200
3 | AF.22230 | Foundation concrete 1x2 aggregate M300 | m3 | 286.5 | 1320000 | 285000 | 48000 | 473584500
4 | AF.61130 | Foundation rebar dia. ≤18 mm | t | 34.2 | 16250000 | 2950000 | 410000 | 670662000
|  | Subtotal foundations | [5 empty] | 1208032200

## Data query
MAIN QUANTITIES SUMMARY — 9-STOREY OFFICE BUILDING |  |  | ← Index
Item | Unit | Quantity
Foundation excavation | m3 | 1250
Foundation concrete (all grades) | m3
Foundation rebar | t

## Variation Register
VARIATION TAKEOFF — GARDEN AND FORECOURT | [5 empty] | ← Index
No. | Variation item | Basis | Unit | Qty | Unit price
1 | Lamp post footing concrete M250 |  | m3 | 8.5 | 1900000
2 | Lamp post footing rebar |  | kg | 420 | 21500
3 | Concrete forecourt omitted | Design change, dwg KT-12 Rev02 | m2 | -65 | 320000
4 | Granite paving to forecourt | Design change, dwg KT-12 Rev02 | m2 | 65 | 680000

## Send Format
QUANTITY SUMMARY | [6 empty] | ← Index
Project: 9-storey office building
Section: Superstructure — columns L1–L3
No. | Work item | Unit | Quantity | Unit price | Amount | Notes
1 | Column concrete M300, 1x2 aggregate | m³ | 86.4 | 1850000 | 159840000
2 | Column reinforcement Ø≤18 | t | 12.85 | 21500000 | 276275000
3 | Column formwork | 100m² | 7.2 | 9800000 | 70560000

## Numbering
FOUNDATION QUANTITIES |  |  |  | ← Index
No. | Work item | Unit | Quantity
| Machine excavation of footings | m³ | 412.6
| Footing concrete B22.5 (M300), comprising: | m³ | 186.2
| - Footing M1 (12 nos) | m³ | 112.8
| - Footing M2 (8 nos) | m³ | 73.4
| Footing rebar D≤18 | t | 12.4
| Footing formwork | m² | 284
| Backfill footings | m³ | 236.5

## Roman
CONSTRUCTION COST SUMMARY |  |  | ← Index
No. | Section | Value (VND)
| Foundations | 4286500000
| Superstructure | 12940000000
| Finishes | 7318200000
| MEP services | 3125600000

## Upper letters
APPENDICES TO THE ACCEPTANCE RECORD |  |  | ← Index
Appendix | Content | Pages
| Foundation as-built drawings | 12
| Foundation construction diary | 26
| Concrete compression test results | 8
| Steel tensile and bend test results | 6
| Material quality certificates (CO/CQ) | 34

## Lower letters
ITEM 2 — SITE ROAD PAVEMENT |  |  |  | ← Index
No. | Layer | Unit | Quantity
| Fine asphalt concrete, 5 cm | m² | 1850
| Coarse asphalt concrete, 7 cm | m² | 1850
| Graded crushed stone type I, 15 cm | m² | 1920
| Graded crushed stone type II, 30 cm | m² | 1980

## Assign Level
DETAILED ESTIMATE — 9-STOREY OFFICE BUILDING |  |  |  | ← Index
Work item | Qty (m³) | Level | Colour legend
Substructure |  |  | Level 1
Earthworks |  |  | Level 2
Machine excavation | 412.6 |  | Level 3
Hand excavation | 45.8
Foundation concrete
Blinding concrete B7.5 (M100) | 18.4
Footing concrete B22.5 (M300) | 186.2
Superstructure

## Filled circle
CONSTRUCTION WORK ACCEPTANCE RECORD |  |  | ← Index
No. | Work items | Result
1 | Erect formwork for columns on grid A-3 Inspect reinforcement before pouring Pour column concrete B22.5 (M300) | Pass
2 | Strip formwork after 2 days Moist-cure the concrete for 7 days | Pass
3 | Take 28-day compression test samples | Pass

## Filled star
INSPECTION AND TEST PLAN (ITP) — FOUNDATIONS |  |  | ← Index
No. | Inspection point | Type
1 | Check pile centre set-out | W
2 | Check pile top level | H
3 | Inspect reinforcement before pouring | H
4 | 28-day compression test | H
5 | Cure pile-cap concrete | W
H = hold point (supervisor must attend); W = witness point

## Minus
UNIT RATE — MATERIAL BREAKDOWN |  |  | ← Index
No. | Work item | Materials
1 | Column concrete B22.5 (M300), 1×2 aggregate | Cement PCB40 Concrete sand 1×2 crushed stone Plasticiser
2 | Hollow-brick wall, cement mortar M75 | Two-hole hollow clay brick Cement PCB40 Masonry sand

## Filled diamond
KEY MILESTONES — 9-STOREY OFFICE BUILDING |  |  | ← Index
No. | Milestone | Date
1 | Bored piles completed | 2026-03-15
2 | Pile caps and ground beams completed | 2026-04-30
3 | Superstructure completed | 2026-08-31
4 | Handover for use | 2026-12-15

## Plus
VARIATION QUANTITIES APPENDIX |  |  |  | ← Index
No. | Description | Unit | Quantity
1 | Extra blinding concrete B7.5 (M100) | m³ | 12
2 | Extra D16 rebar for ground beams | kg | 850
3 | Extra pile-cap side formwork | m² | 45

## Asterisk
TENDER PRICE SUMMARY |  |  | ← Index
No. | Section | Amount (VND)
1 | Foundations | 4286500000
2 | Superstructure | 12940000000
3 | Finishes | 7318200000
Total |  | 24544700000
Notes: | Unit rates exclude VAT Provisional value, settled on actual quantities Applies to quantities accepted before 31/12/2026

## Checkbox
PRE-POUR CHECKLIST — LEVEL 3 SLAB |  |  | ← Index
No. | Check item | Notes
1 | Bar sizes and spacing as per drawings
2 | Spacers in place, correct concrete cover
3 | Formwork tight and firmly propped
4 | Formwork cleaned and wetted

## Checked
FOUNDATION COMPLETION — ACCEPTANCE DOCUMENTS |  |  | ← Index
No. | Document | Submitted
1 | ☐ Foundation rebar acceptance record | 2026-10-05
2 | ☐ 28-day compression test results | 2026-10-05
3 | ☐ Foundation construction diary | 2026-10-06
4 | ☐ Foundation as-built drawings

## Rejected
INCOMING MATERIAL CHECK — STEEL LOT OF 12/08/2026 |  |  | ← Index
No. | Check item | Notes
1 | ☑ CO/CQ certificates complete
2 | ☑ Labels and bar sizes match the order
3 | ☐ No surface rust, no bent bars | Surface rust on bundle 3
4 | ☐ Tensile test results meet the spec | D16 sample failed

## Remove bullets
BORED PILE METHOD STATEMENT |  | ← Index
No. | Sequence
1 | ● Clear the site, set out pile centres ● Bore to the design level ● Lower the cage, pour concrete
2 | − Check the borehole depth − Measure the base sediment
3 | ★ Pile concrete B30 (M400)

## Number list
FOUNDATION TASK LIST |  |  | ← Index
Task | Start | Days
Excavate footings, grids A-D | 2026-03-02 | 6
Pour blinding concrete | 2026-03-09 | 2
Fabricate pile-cap rebar Fix pile-cap rebar | 2026-03-11 | 5
Pour pile-cap concrete | 2026-03-17 | 2

## Roman list
QUANTITY SUMMARY |  | ← Index
Section | Value (VND)
Earthworks | 386400000
Concrete works | 2915700000
Reinforcement works | 1842300000
Formwork | 624900000

## Upper letters list
SUPERSTRUCTURE METHOD STATEMENT |  | ← Index
Section | Page
Site preparation | 3
Formwork and scaffolding | 7
Reinforcement method | 15
Health, safety and environment | 22

## Lower letters list
PILE-CAP REINFORCEMENT |  |  | ← Index
Task | Unit | Quantity
Fabricate pile-cap rebar | t | 18.6
Fix pile-cap rebar | t | 18.6
Tie cover spacers | pcs | 1240
Weld D25 bar splices | joints | 96

## Remove list numbering
FOUNDATION QUANTITIES |  |  | ← Index
Work item | Unit | Quantity
1. Machine excavation of footings | m³ | 412.6
2. Blinding concrete B7.5 (M100) | m³ | 18.4
3. Footing rebar, fabricate and fix | t | 18.6
3. Pile-cap formwork | m² | 96.5

## Multilevel 1.1.1
DETAILED ESTIMATE — 9-STOREY OFFICE BUILDING |  |  | ← Index
Item | Unit | Quantity
Substructure
Earthworks
Machine excavation | m³ | 412.6
Hand excavation | m³ | 45.8
Foundation concrete
Blinding concrete B7.5 (M100) | m³ | 18.4
Footing concrete B22.5 (M300) | m³ | 186.2
Superstructure

## Remove multilevel numbering
DETAILED ESTIMATE — 9-STOREY OFFICE BUILDING |  |  | ← Index
Item | Unit | Quantity
1. Substructure
1.1. Earthworks
1.1.1. Machine excavation | m³ | 412.6
1.1.2. Hand excavation | m³ | 45.8
2. Superstructure

## Sentence case
No. | Work description | ← Index
1 | pour column concrete, level 3. inspect before pouring
2 | INSTALL BEAM AND SLAB FORMWORK PER TCVN 4453
3 | note: check level of column C1
4 | concrete strength reaches 30 MPa. sample per TCVN 3105

## UPPERCASE
Construction work acceptance record | ← Index
Concreting of level-3 columns
Owner: Project Management Unit No. 2
Concrete B25, strength 30 MPa

## lowercase
No. | Work item | ← Index
1 | REINFORCED CONCRETE FOOTING M1
2 | HDPE PIPE D110 PER TCVN 7305
3 | Lean Concrete With 4x6 Stone
4 | Concrete Strength 30 MPa

## Proper Case
No. | Name / Company | Role | ← Index
1 | nguyễn văn an | Site manager
2 | TRẦN THỊ BÌNH | QA/QC engineer
3 | lê Hoàng nam | Foreman
4 | HOANG LONG CONSTRUCTION JSC | Subcontractor
5 | site team QA/QC block C1 | Crew

## SMART case (AI)
No. | Description | ← Index
1 | acceptance of beam and slab rebar per tcvn 5574:2018
2 | contractor: hoang long construction jsc
3 | supervisor: engineer nguyen van an

## Italic
No. | Work item | Unit | Quantity | ← Index
1 | Bê tông lót móng M150 Lean concrete M150 | m3 | 12.5
2 | Bê tông móng M300 Footing concrete M300 | m3 | 86.4
3 | Bê tông cột M300 Column concrete M300 | m3 | 24.6
4 | Ván khuôn cột Column formwork | m2 | 182

## Text Reverse
No. | Work item | Unit | ← Index
1 | Lean concrete for footing - AF.11110 | m3
2 | Footing rebar D≤10 - AF.61110 | t
3 | Footing formwork - AF.81110 | m2

## Font Change
TT / No. | Công việc nghiệm thu / Inspected work | Tiêu chuẩn / Standard | Kết quả / Result | ← Index
1 | Level-3 beam & slab rebar | TCVN 4453:1995 | Pass
2 | Level-3 beam & slab formwork | TCVN 4453:1995 | Pass
3 | Level-3 column concrete | TCVN 4453:1995 | Pass

## Remove extra spaces
No. | Work item | Length | ← Index
1 | Footing concrete M250 | 26
2 | Footing rebar D≤10 | 21
3 | Column formwork | 19

## Add text
No. | Work item | Unit | Quantity | ← Index
1 | Lean concrete with 4x6 stone | m3 | 3.2
2 | Footing rebar D≤10 | t | 0.85
3 | Footing formwork | m2 | 14.4

## Remove accents
No. | Item | Accepted | ← Index
1 | Móng đơn trục A-1 | 2026-03-12
2 | Bê tông cốt thép dầm sàn tầng 2 | 2026-03-26
3 | Đường ống cấp nước D110 | 2026-04-09

## Add accents (AI)
Date | Work done | ← Index
2026-10-06 | tap ket vat tu gach xay tuong
2026-10-06 | Vệ sinh mặt bằng cuối ngày
2026-10-07 | nghiem thu cot thep dam san tang 3
2026-10-08 | do be tong dam san tang 3

## Auto format
No. | Work item | Unit | Quantity | Accepted | ← Index
1 | Footing concrete M250 | m3 | 125.5 | 15/03/2026
2 | Footing rebar | kg | 1,200 | 18/03/2026
3 | Footing formwork | m2 | 86.25 | 2026-03-20
4 | Footing excavation | m3 | 42 | 22/03/2026
| Total |  | 0

## Superscript
No. | Work item | Unit | Quantity | ← Index
1 | Footing concrete M250 | m3 | 42.5
2 | Footing formwork | m2 | 86.4
3 | Footing rebar D≤10 | t | 1.25
4 | Wall plaster 15 mm thick | m2 | 320
5 | Footing excavation | m3 | 156

## Subscript
No. | Component / test item | ← Index
1 | Water H2O
2 | Slaked lime Ca(OH)2
3 | Carbon dioxide CO2 (carbonation)
4 | Fe3+ ion in mixing water
5 | Concrete B25, mortar M300

## Bulk find - replace…
DETAILED COST ESTIMATE — SUPERSTRUCTURE |  |  |  | ← Index
No. | Description of work | Unit | Quantity
1 | Lean concrete under footings, M100 | m³ | 12.6
2 | RC footings, 1x2 aggregate, M250 | m³ | 48.3
3 | RC columns, level 1, M300 | m³ | 18.7
4 | RC beams and slab, level 2, M300 | m³ | 96.4
5 | Formwork to columns, level 1 | m² | 210.5
6 | Rebar to columns, level 1, D≤18 | t | 3.85

## Smart Data Cleaning…
Code | Material | Unit | Qty | ← Index
VT01 | portland cement PCB40 | kg | 18000
VT02 | REBAR CB400-V D16 | kg | 4520
VT03 | plastering sand | m3 | 42
VT01 | Portland cement PCB40 | kg | 18000
VT04 | porcelain floor tile 600x600 | m2 | 350
VT03 | Plastering sand | m3 | 42
VT05 | Crushed stone 1x2 | m3 | 65

## Encoding
BAÛNG KHOÁI LÖÔÏNG PHAÀN MOÙNG |  |  |  | ← Index
TT | Noäi dung coâng vieäc | ÑVT | Khoái löôïng
1 | Coâng taùc beâ toâng loùt M100 | m3 | 12.6
2 | Coát theùp moùng D<=18 | taán | 4.85
3 | Vaùn khuoân moùng | m2 | 86.4
4 | Beâ toâng moùng M250 | m3 | 48.3

## To Unicode
TT | Néi dung c«ng viÖc | §VT | KL | ← Index
1 | C«ng t¸c bª t«ng lãt M100 | m3 | 12.6
2 | Cèt thÐp dÇm sµn D<=10 | kg | 1250
3 | V¸n khu«n cét vu«ng | m2 | 86.4
4 | Bª t«ng cét M300 | m3 | 18.7

## To VNI
TT | Nội dung công việc | ĐVT | Khối lượng | ← Index
1 | Bê tông móng đá 1x2 M250 | m3 | 48.3
2 | Ván khuôn cột, vách | m2 | 210.5
3 | Thép tròn D18 trở lên | tấn | 3.85
4 | Xây tường gạch ống dày 200 | m3 | 26.4

## To TCVN3
TT | Nội dung công việc | ĐVT | Khối lượng | ← Index
1 | Đào móng bằng thủ công | m3 | 35.2
2 | Lắp dựng cốt thép cột | tấn | 2.15
3 | Ván khuôn dầm, sàn | m2 | 320
4 | Đổ bê tông sàn M250 | m3 | 64.8

## Translate
BILL OF QUANTITIES — FOUNDATIONS |  |  |  | ← Index
Item | Description | Unit | Qty
1 | Lean concrete grade C10, 100 mm thick | m³ | 12.6
2 | Reinforced concrete pile caps, C30 | m³ | 48.3
3 | Formwork to ground beams | m² | 210.5
4 | Deformed bars CB400-V, D16–D25 | t | 3.85

## Quick Input
SITE DIARY — 9-STOREY OFFICE BUILDING |  |  | ← Index
Date | Crew | Work item
2026-10-05 | Concrete crew 1 | Concrete slab level 3
2026-10-05 | Rebar crew | Fix column reinforcement
2026-10-06 | Masonry crew 2 | Brickwork grid A
2026-10-06 | Formwork crew | Formwork beams and slab L4
2026-10-07 | Rebar crew | Fix column reinforcement
2026-10-07 | Concrete crew 1 | Pour columns level 4
2026-10-08

## Auto-suggest on cell select
← Index
MATERIAL QUANTITIES — 9-STOREY OFFICE BUILDING
No. | Code | Material | Unit | Unit price | Quantity
1 | XM01 | Portland cement PCB40 | kg | 1650 | 18000
2 | TH16 | Rebar CB400-V D16 | kg | 15200 | 4520
3
4

## Configure source ranges…
Code | Material | Unit | Unit price | ← Index
XM01 | Portland cement PCB40 | kg | 1650
XM02 | Portland cement PCB30 | kg | 1450
TH16 | Rebar CB400-V D16 | kg | 15200
CV01 | Plastering sand | m3 | 320000
DA12 | Crushed stone 1x2 | m3 | 410000
GO60 | Porcelain tile 600x600 | m2 | 185000
GR02 | Hollow clay brick | pcs | 1250

## Insert Rows
SUPERSTRUCTURE QUANTITIES — 9-STOREY OFFICE BUILDING |  |  |  | ← Index
No. | Work item | Unit | Quantity
1 | Level-3 column concrete, M300 | m³ | 18.2
2 | Level-3 beam & slab concrete, M300 | m³ | 64.5
3 | Level-3 column rebar, CB400-V | t | 3.85
4 | Level-3 beam & slab rebar, CB400-V | t | 9.12
5 | Level-3 column formwork | m² | 142
6 | Level-3 beam & slab formwork | m² | 516

## Insert Columns
ACCEPTED QUANTITIES LOG — 9-STOREY OFFICE BUILDING |  |  |  | ← Index
No. | Work item | Unit | Contract qty
1 | Machine excavation of footing pits | m³ | 1250
2 | Blinding concrete M100 | m³ | 38.5
3 | Footing concrete M300 | m³ | 412.6
4 | Footing rebar CB400-V | t | 36.8
5 | Footing formwork | m² | 864

## Insert and Copy
DETAILED ESTIMATE — FOUNDATIONS |  |  |  | ← Index
No. | Work item | Unit | Quantity
1 | Footing concrete M300 | m³ | 412.6
2 | Ground beam concrete M300 | m³ | 58.4
- Materials
- Labour
- Plant

## Delete blanks
FOUNDATION QUANTITIES (exported from estimating software) |  |  |  | ← Index
No. | Work item | Unit | Quantity
1 | Blinding concrete M100 | m³ | 38.5
2 | Footing concrete M300 | m³ | 412.6
3 | Footing rebar CB400-V | t | 36.8
4 | Footing formwork | m² | 864

## Delete hidden rows
QUANTITY SUMMARY — 9-STOREY OFFICE BUILDING |  |  |  |  | ← Index
No. | Package | Work item | Unit | Quantity
1 | Steelwork | Steel column I300 | t | 12.4
2 | Concrete | Level-2 slab concrete, M300 | m³ | 96.5
3 | Steelwork | Steel beam I400 | t | 18.75
4 | Steelwork | Anchor bolts M24 | set | 64
5 | Finishes | Internal wall plaster | m² | 1240
6 | Concrete | Level-2 column concrete, M300 | m³ | 22.8
7 | Steelwork | Anti-rust paint on steelwork | m² | 486
8 | Finishes | 600x600 floor tiling | m² | 815

## Delete unused formats
SHELL QUANTITIES — 9-STOREY OFFICE BUILDING |  |  |  |  | ← Index
No. | Work item | Unit | Quantity | Amount (VND)
1 | Columns L1–L3 concrete, M300 | m³ | 54.6 | 68250000
2 | Beams & slabs L1–L3, M300 | m³ | 193.5 | 241875000
3 | Rebar CB400-V | t | 38.9 | 700200000
4 | Formwork to columns, beams, slabs | m² | 1820 | 309400000
5 | 220 mm hollow brick walls | m³ | 86.2 | 112060000

## Merge keep data
QUANTITY NOTES — FOUNDATIONS |  |  |  | ← Index
No. | Quantity description | Unit | Quantity
1 | Blinding concrete 4x6 stone M100 | m³ | 12.5
100 mm thick, volume 12,5 m³
Location: footings M1, M2 (grid 1–3)
2 | Footing concrete M300 | m³ | 412.6

## Merge similar
REBAR SCHEDULE — FOOTINGS, LEVEL-1 COLUMNS |  |  |  |  | ← Index
Member | Mark | Diameter | Length (mm) | Bars
Footing M1 | 1 | ø16 | 2350 | 24
Footing M1 | 2 | ø12 | 2350 | 24
Footing M1 | 3 | ø8 | 1420 | 36
Column C1 | 4 | ø20 | 3900 | 8
Column C1 | 5 | ø8 | 1560 | 30
Column C1 | 6 | ø8 | 980 | 30

## Merge rows by key
CONCRETE TAKE-OFF BY MEMBER |  |  | ← Index
Work code | Quantity | Location
AF.11110 | 12.5 | Footing M1
AF.11110 | 8.4 | Footing M2
AF.12220 | 6.2 | Column C1
AF.11110 | 6.3 | Footing M3
AF.12220 | 5.9 | Column C2
AF.13110 | 24.6 | Beam D1

## Auto group
BILL OF QUANTITIES — 9-STOREY OFFICE BUILDING |  |  |  | ← Index
Ref. | Work item | Unit | Quantity
1 | SUBSTRUCTURE
1.1 | Earthworks
1.1.1 | Machine excavation of footing pits | m³ | 1250
1.1.2 | Backfill to K95 compaction | m³ | 640
1.2 | Foundation concrete
1.2.1 | Blinding concrete M100 | m³ | 38.5
1.2.2 | Footing concrete M300 | m³ | 412.6
2 | SUPERSTRUCTURE
2.1 | Columns L1–L3 concrete, M300 | m³ | 54.6
2.2 | Beams & slabs L1–L3, M300 | m³ | 193.5

## AutoFit merged
CONSTRUCTION WORK ACCEPTANCE RECORD |  | ← Index
1. Work accepted:
Rebar to footings M1, M2 — main bars ø18 grade CB400-V, links ø8 at 150; type, number, spacing and concrete cover checked.
2. Inspection time:
Start 08:00 on 08/10/2026 — end 10:30 on 08/10/2026
3. Assessment of the work done:
Work complies with shop drawings KC-03 to KC-07, TCVN 4453:1995 and the project specification; ready for formwork erection and footing concreting.

## Select visible
BILL OF QUANTITIES — 9-STOREY OFFICE BUILDING |  |  |  |  | ← Index
No. | Package | Work item | Unit | Quantity
1 | Substructure | Footing concrete M300 | m³ | 412.6
2 | Substructure | Footing rebar CB400-V | t | 36.8
3 | Superstructure | Columns L1–L3 concrete, M300 | m³ | 54.6
4 | Superstructure | Beams & slabs L1–L3, M300 | m³ | 193.5
5 | Substructure | Footing formwork | m² | 864
6 | Superstructure | Rebar to columns, beams, slabs CB400-V | t | 38.9
7 | Superstructure | Formwork to columns, beams, slabs | m² | 1820
8 | Substructure | Backfill to K95 | m³ | 640

## Copy-Paste visible
ACCEPTED QUANTITIES — SUPERSTRUCTURE |  |  |  |  | ← Index
Mark | Member | Level | Unit | Actual qty
C4-01 | Column grid A-1 | Level 4 | m³
C5-01 | Column grid A-1 | Level 5 | m³
C4-02 | Column grid A-2 | Level 4 | m³
C5-02 | Column grid A-2 | Level 5 | m³
D4-01 | Beam grid A, bay 1–2 | Level 4 | m³
D5-01 | Beam grid A, bay 1–2 | Level 5 | m³
S4-01 | Slab panel S1 | Level 4 | m³
S5-01 | Slab panel S1 | Level 5 | m³

## Join Text
TT | Sheet code | Form | Sheets to print | ← Index
1 | YCNTCV | Request for work inspection
2 | BBNTCV | Construction work acceptance record
3 | KT_DD | Dimensional survey check sheet

## Join Merged
WORK ACCEPTANCE RECORD |  |  | ← Index
Project: | 9-storey office building | Cells to swap
Work item: | Footing concrete M1, M2
Location: | Grid 1–3 / A–C
Inspection date: | 2026-10-08

## Formula View
LEVEL 5 QUANTITY SUMMARY |  |  |  |  | ← Index
No. | Code | Work item | Unit | Level 5
1 | AF.12315 | Column concrete M300 | m³ | 18.46
2 | AF.12415 | Beam and slab concrete M300 | m³ | 96.8
3 | AF.61531 | Beam and slab rebar d ≤ 18 mm | t | 0
4 | AF.86311 | Beam and slab formwork | 100m² | 7.92

## KL Tang 4
DETAILED QUANTITIES — LEVEL 4 |  |  |  |  | ← Index
No. | Description | Code | Unit | Quantity
1 | Columns grid A | AF.12315 | m³ | 9.1
2 | Columns grid B | AF.12315 | m³ | 9.1
3 | Beams & slab zone 1 | AF.12415 | m³ | 56.4
4 | Beams & slab zone 2 | AF.12415 | m³ | 37.2
5 | Lift core walls | AF.12515 | m³ | 12.6
6 | Beam & slab formwork | AF.86311 | 100m² | 7.64
7 | Wall formwork | AF.86411 | 100m² | 2.18
8 | Beam & slab rebar zone 1 | AF.61531 | t | 5.9
9 | Beam & slab rebar zone 2 | AF.61531 | t | 3.55

## KL Tang 5
DETAILED QUANTITIES — LEVEL 5 |  |  |  |  | ← Index
No. | Description | Code | Unit | Quantity
1 | Columns grid A | AF.12315 | m³ | 9.23
2 | Columns grid B | AF.12315 | m³ | 9.23
3 | Beams & slab zone 1 | AF.12415 | m³ | 58.3
4 | Beams & slab zone 2 | AF.12415 | m³ | 38.5
5 | Beam & slab rebar zone 1 | AF.61531 | t | 6.15
6 | Beam & slab rebar zone 2 | AF.61531 | t | 3.7
7 | Beam & slab formwork | AF.86311 | 100m² | 7.92

## Lookup Trace
DETAILED ESTIMATE — FOUNDATIONS | [5 empty] | ← Index
No. | Code | Work item | Unit | Quantity | Unit rate
1 | AB.11213 | Manual excavation, soil grade III | m³ | 42.5 | 285000
2 | AF.11120 | Blinding concrete M100, 4x6 stone | m³ | 12.4 | 1320000
3 | AF.11220 | Footing concrete M250, 1x2 stone | m³ | 86.5 | 1850000
4 | AF.61120 | Footing rebar d ≤ 18 mm | t | 7.85 | 21500000
5 | AF.81122 | Footing formwork | 100m² | 2.1 | 6240000

## RATES
DETAILED UNIT RATES |  |  |  | ← Index
Project: 9-storey office building
Code | Work item | Unit | Unit rate
AB.11213 | Manual excavation, soil grade III | m³ | 285000
AF.11120 | Blinding concrete M100 | m³ | 1320000
AF.11210 | Footing concrete M200 | m³ | 1710000
AF.11220 | Footing concrete M250 | m³ | 1850000
AF.61120 | Footing rebar d ≤ 18 mm | t | 21500000
AF.81122 | Footing formwork | 100m² | 6240000

## Dependents
SCHEDULE CALCULATION PARAMETERS |  |  |  | ← Index
No. | Parameter | Value | Unit
1 | Machine-shift factor | 1.15 | -
2 | Labour factor | 1.05 | -
3 | Working hours per shift | 8 | h

## Autosum
STRUCTURAL CONCRETE QUANTITIES — 9-STOREY OFFICE BUILDING |  |  |  | ← Index
Section | Work item | Unit | Quantity
FOUNDATION
| Blinding concrete M100 | m³ | 12.4
| Footing concrete M250 | m³ | 86.5
| Ground beam concrete M250 | m³ | 18.3
FRAME
| Level 1 column concrete M300 | m³ | 34.2
| Level 2 beam and slab concrete M300 | m³ | 96.8
| Staircase concrete M300 | m³ | 6.45

## Fill Results
FOUNDATION TAKE-OFF — 9-STOREY OFFICE BUILDING |  |  |  | ← Index
No. | Description | Unit | Quantity
1 | Footing pits F1: 4 pits x 2.5 x 2.5 x 1.6 | m³ | 40
2 | Ground beams: 2 x 18.4 x 0.4 x 0.5 | m³ | 7.36
3 | Blinding: 4 x 2.7 x 2.7 x 0.1 | m³ | 2.92
4 | Column stubs C1: 4 x 0.3 x 0.3 x 1.2 | m³ | 0.43

## Direct Ref
BILL OF QUANTITIES — FOUNDATIONS |  |  |  |  | ← Index
No. | Code | Work item | Quantity | Unit rate
1 | AB.11213 | Manual excavation, soil grade III | 42.5
2 | AF.11120 | Blinding concrete M100 | 12.4
3 | AF.11220 | Footing concrete M250 | 86.5
4 | AF.61120 | Footing rebar d ≤ 18 mm | 7.85
5 | AF.8112 | Footing formwork | 2.1

## DON GIA
DETAILED UNIT RATES — FOUNDATIONS |  |  |  | ← Index
Code | Work item | Unit | Unit rate
AB.11213 | Manual excavation, soil grade III | m³ | 285000
AF.11120 | Blinding concrete M100 | m³ | 1320000
AB.13112 | Backfill to footing pits, compaction K = 0.90 | m³ | 96000
AF.11220 | Footing concrete M250 | m³ | 1850000
AF.61120 | Footing rebar d ≤ 18 mm | t | 21500000
AF.81122 | Footing formwork | 100 m² | 7650000

## Rounding Func
MEMBER CONCRETE QUANTITIES — LEVEL 1 | [6 empty] | ← Index
No. | Member | Qty | L (m) | W (m) | H (m) | Vol. (m³)
1 | Footing F1 | 4 | 2.45 | 2.45 | 0.75 | 18.0075
2 | Ground beam GB1 | 2 | 18.35 | 0.35 | 0.55 | 7.0648
3 | Column stub C1 | 4 | 0.33 | 0.33 | 1.15 | 0.50094
4 | Beam B1 | 6 | 5.65 | 0.22 | 0.45 | 3.3561
5 | Slab S1 | 1 | 12.45 | 7.85 | 0.12 | 11.7279

## Lock Ref
LEVEL 3 SLAB REBAR SCHEDULE |  |  |  |  | ← Index
Mark | Dia. (mm) | Bars | Bar length (m) | Weight (kg)
S1 | 10 | 45 | 6.2 | 172.14
S2 | 10 | 38 | 4.85 | 113.71
S3 | 12 | 26 | 7.4 | 170.85
S4 | 8 | 60 | 2.35 | 55.7
S5 | 14 | 12 | 5.9 | 85.67

## BANGTHEP
Dia. (mm) | kg/m | ← Index
6 | 0.222
8 | 0.395
10 | 0.617
12 | 0.888
14 | 1.21
16 | 1.58
18 | 2
20 | 2.47
22 | 2.98
25 | 3.85
28 | 4.83

## Error Check
COST SUMMARY — 9-STOREY OFFICE BUILDING |  |  |  |  | ← Index
No. | Item | Quantity | Unit rate | Amount
I | FOUNDATIONS |  |  | 206033000
1 | Blinding concrete M100 | 12.4 | 1320000 | 16368000
2 | Footing concrete M250 | 86.5 | 1850000 | 160025000
3 | Footing formwork | 4.75 | 6240000 | 29640000
II | SUPERSTRUCTURE |  |  | 242350000
1 | Column, beam, slab concrete M300 | 131 | 1850000 | 242350000

## Color Shapes
LEVEL 3 SLAB POUR PROGRESS |  |  |  |  | ← Index
Shape name | Colour code | Status | Pour date | Location
O_A1 | 5296274 | Poured | 2026-09-18 | Grid 1–2 × A–B
O_A2 | 5296274 | Poured | 2026-09-18 | Grid 2–3 × A–B
O_B1 | 65535 | In progress | 2026-10-08 | Grid 1–2 × B–C
O_B2 | 65535 | In progress | 2026-10-08 | Grid 2–3 × B–C
O_C1 | 12632256 | Not started |  | Grid 1–2 × C–D
O_C2 | 12632256 | Not started |  | Grid 2–3 × C–D

## Color Rects
LEVEL 5 SLAB POURS BY WEEK | [6 empty] | ← Index
Zone | Pour wk | Construction week
|  | 1 | 2 | 3 | 4 | 5
S1 | 2 | 12632256 | 65535 | 5296274 | 5296274 | 5296274
S2 | 3 | 12632256 | 12632256 | 65535 | 5296274 | 5296274
S3 | 4 | 12632256 | 12632256 | 12632256 | 65535 | 5296274
S4 | 5 | 12632256 | 12632256 | 12632256 | 12632256 | 65535

## List Shapes
SHAPE LIST — LEVEL 3 PLAN | ← Index
Shape name

## Rename Shapes
RENAME PILE CAPS |  | ← Index
Old name | New name
Rectangle 12 | DM_A1
Rectangle 13 | DM_A2
Rectangle 14 | DM_B1
Rectangle 15 | DM_B2
Rectangle 16 | DM_C1

## Get Position
SITE FACILITY POSITIONS |  | ← Index
Shape name | Top;Left
SiteOffice
Warehouse
PrecastYard
MainGate

## Linked Labels
FOOTING POUR TRACKING |  |  | ← Index
Footing | Colour code | Pour date
1 | 5296274 | 2026-09-20
2 | 5296274 | 2026-09-21
3 | 5296274 | 2026-09-22
4 | 5296274 | 2026-09-24
5 | 5296274 | 2026-09-26
6 | 5296274 | 2026-09-29
7 | 65535 | 2026-10-06
8 | 65535 | 2026-10-07
9 | 12632256
10 | 12632256
11 | 12632256
12 | 12632256

## Plan progress
PLAN PROGRESS TRACKING | [8 empty] | ← Index
Plan: | Pile plan |  | Data date: | 2026-10-08 | Transparency (%) | 30
[5 empty] | Status | Colour | Count | Share
No. | Shape name | Status | Date | Note | Not started |  | 3 | 37.5%
1 | P1 | Accepted | 2026-10-02 |  | In progress |  | 1 | 12.5%
2 | P2 | Completed | 2026-10-03 |  | Completed |  | 3 | 37.5%
3 | P3 | Completed | 2026-10-03 |  | Accepted |  | 1 | 12.5%
4 | P4 | Completed | 2026-10-05
5 | P5 | In progress | 2026-10-08 | Rig no. 2
6 | P6 | Not started
7 | P7 | Not started
8 | P8 | Not started

## Get Color Code
PROGRESS COLOURS — 9-STOREY OFFICE BUILDING |  |  |  | ← Index
TT | Work package | Standard colour | Colour code
1 | Substructure
2 | Superstructure
3 | Finishes

## Auto Click
STT | Timestamp (ms) | X | Y | Wait (ms) | ← Index
1 | 18452310 | (record) | (record) | 0
2 | 18454120 | (record) | (record) | 1810
3 | 18455985 | (record) | (record) | 1865
4 | 18458410 | (record) | (record) | 2425

## Pictures
SITE PHOTO LOG — WEEK 41/2026 |  |  |  | ← Index
Project: 9-storey office building
No. | Work item / location | Site photo | Remarks
1 | Rebar fixing, level-3 slab, grid 1-3 |  | Accepted 06/10
2 | Beam formwork, level 3, grid A-B |  | Awaiting supervisor
3 | Concreting footing M3, B25 |  | 2 sample sets taken
4 | External walls, level 2 |  | Passed

## Insert by Name
PRECAST ELEMENT PHOTO LOG |  |  |  | ← Index
Project: 9-storey office building
No. | Element code (photo name) | Photo | Cast on
1 | CK-001 |  | 2026-10-02
2 | CK-002 |  | 2026-10-03
3 | CK-003.jpg |  | 2026-10-05
4 | CK-004 |  | 2026-10-06

## Pic Comment
LEVEL-2 SLAB REBAR SCHEDULE | [5 empty] | ← Index
No. | Slab bay | Bars | Count | KL (kg) | Site remark
1 | Grid A-B / 1-2 | Ø10a150 | 86 | 212.4 | Bottom mesh
2 | Grid B-C / 1-2 | Ø10a150 | 86 | 212.4
3 | Grid A-B / 2-3 | Ø12a200 | 64 | 227.3
4 | Grid B-C / 2-3 | Ø12a200 | 64 | 227.3

## Comment by Name
LEVEL-5 MASONRY INSPECTION REGISTER |  |  |  |  | ← Index
Record | Work | Location | Date | Result
NT-501 | 220 mm brick wall | Grid 1-2 | 2026-10-01 | Pass
NT-502 | 220 mm brick wall | Grid 2-3 | 2026-10-02 | Pass
NT-503 | 110 mm brick wall | Grid A-B | 2026-10-03 | Pass
NT-504 | Door lintels | Grid B-C | 2026-10-05 | Pass
NT-505 | Internal plastering | Grid 1-3 | 2026-10-07 | Pending

## Move-Resize
SITE DIARY — WEEK 41/2026 |  |  |  | ← Index
Date | Work | Photo | Remarks
2026-10-06 | Concreting footing M2, B25 | 📷 M2.jpg | 18 m³ — 2 sample sets
2026-10-07 | Concreting footing M3, B25 |  | 21 m³ — 2 sample sets
📷 M3.jpg

## Capture and Annotate
WEEKLY SITE MEETING MINUTES — WEEK 41/2026 |  | ← Index
Project: 9-storey office building
1. | Foundation progress: 85 % of plan.
2. | Supervisor: pile-cap ĐM-4 bottom level on the shop drawing differs from design.
3. | Contractor to check and resubmit before 10/10/2026.
Illustration:

## Polygon Cloud
LEVEL-3 SLAB REBAR — STRENGTHENING ZONE |  |  | ← Index
| Extra bars | OPENING
Ø12a100

## Cloud Around Selection
INTERIM PAYMENT 3 — QUANTITIES | [5 empty] | ← Index
Project: 9-storey office building
No. | Code | Description | Unit | IPC 2 | IPC 3
1 | AB.25112 | Machine excavation, soil class II | m³ | 412.5 | 412.5
2 | AF.11114 | Blinding concrete M100 | m³ | 18.6 | 21.3
3 | AF.22224 | Footing concrete M300 | m³ | 186.4 | 186.4
4 | AF.61120 | Footing rebar Ø ≤ 18 mm | t | 14.82 | 14.82
5 | AF.81111 | Footing formwork | 100m² | 3.46 | 3.92
6 | AE.22214 | 220 mm brick wall, mortar M75 | m³ | 96 | 96
7 | AK.21224 | Internal plaster 15 mm | m² | 1240 | 1240
8 | AK.84114 | Internal paint, 1 primer + 2 coats | m² | 1240 | 1315

## File List
SHOP DRAWING REGISTER — STRUCTURAL PACKAGE | ← Index
Project: 9-storey office building
Attached to transmittal No. 15/2026

## Split table
SUMMARY OF QUANTITIES — 9-STOREY OFFICE BUILDING |  |  |  |  | ← Index
No. | Package | Work item | Unit | Quantity
1 | Foundation | Foundation excavation | m³ | 412.6
2 | Foundation | Blinding concrete M100 | m³ | 18.4
3 | Foundation | Footing concrete B25 | m³ | 126.3
4 | Foundation | Footing rebar CB400-V | t | 9.85
5 | Superstructure | Column concrete B30 | m³ | 38.7
6 | Superstructure | Beam & slab concrete B30 | m³ | 164.2
7 | Superstructure | Beam & slab rebar CB400-V | t | 21.6
8 | Superstructure | Beam & slab formwork | m² | 1142.5
9 | Finishes | 220 hollow-brick wall | m³ | 96.8
10 | Finishes | Internal plaster, mortar M75 | m² | 2316
11 | Finishes | Granite floor tiles 600x600 | m² | 845
12 | Finishes | Interior wall painting | m² | 2316

## Compare sheets
Sheet comparison | Estimate_Issued.xlsx / Estimate | ↔ | Estimate_Returned.xlsx / Estimate | ← Index
Cells compared | 65 | Different | 8
Cell | In A | In B | Kind
E6 | 125000 | 128500 | different
E9 | 365000 | 392000 | different
D11 | 145 | 152 | different
A13 |  | 10 | only in B
B13 |  | Toilet floor waterproofing | only in B
C13 |  | m² | only in B
D13 |  | 86 | only in B
E13 |  | 245000 | only in B

## Merge tables
BILL OF QUANTITIES — 9-STOREY OFFICE BUILDING |  |  |  |  | ← Index
No. | Code | Work item | Unit | Quantity
1 | AB.25112 | Machine excavation of footings |  | 412.6
2 | AF.11113 | Blinding concrete M100 |  | 18.4
3 | AF.61120 | Footing rebar d ≤ 18 |  | 9.85
4 | AF.11213 | Footing concrete B25 |  | 126.3
5 | AF.81122 | Footing formwork |  | 236
6 | AE.22223 | 220 hollow-brick wall |  | 96.8
7 | AK.21224 | Internal plaster, mortar M75 |  | 2316
8 | AK.5122 | Granite floor tiles 600x600 |  | 845

## Rates (2)
COMPANY UNIT RATES — Q4/2026 |  |  |  | ← Index
Code | Work item | Unit | Unit rate
AB.11213 | Manual excavation of footings, soil grade III | m³ | 285000
AB.25112 | Machine excavation of footings | m³ | 86500
AE.22223 | Hollow brick wall 220 | m³ | 1580000
AF.11113 | Blinding concrete M100 | m³ | 1150000
AF.11213 | Footing concrete B25 | m³ | 1680000
AF.61120 | Footing rebar d ≤ 18 | t | 23400000
AF.81122 | Footing formwork | m² | 165000
AK.21224 | Interior wall plastering, mortar M75 | m² | 98000
AK.51223 | Granite floor tiles 600x600 | m² | 312000
AK.84112 | Interior wall painting | m²

## Rename Files
← Index
Old name | New name
IMG_2841.JPG | NT-501_dam_truc-A.jpg
IMG_2842.JPG | NT-501_dam_truc-B.jpg
IMG_2843.JPG | NT-502_san_S1.jpg
IMG_2844.JPG | NT-502_san_S2.jpg
IMG_2845.JPG | NT-503_cot_C3.jpg

## Create Hyperlink
CONSTRUCTION DRAWING LIST — ARCHITECTURE |  |  |  | ← Index
No. | Ref. | Drawing title | File path
1 | KT-01 | Level 1 plan | D:\DuAn\NhaVanPhong\TKBVTC\KT-01.pdf
2 | KT-02 | Levels 2–8 plan | D:\DuAn\NhaVanPhong\TKBVTC\KT-02.pdf
3 | KT-03 | Elevation, grid 1–8 | D:\DuAn\NhaVanPhong\TKBVTC\KT-03.pdf
4 | KT-04 | Section A-A | D:\DuAn\NhaVanPhong\TKBVTC\KT-04.pdf
5 | KT-05 | Staircase details | D:\DuAn\NhaVanPhong\TKBVTC\KT-05.pdf

## Create Folder
← Index
NhaVanPhong9T | 01_HoSoPhapLy | HopDong
GiayPhepXD
| 02_TKBVTC | KienTruc
KetCau
MEP
| 03_NghiemThu | Thang_09
Thang_10
04_NhatKy

## Transcribe Audio
SITE COORDINATION MEETING MINUTES | ← Index
5 Oct 2026 — 9-storey office building
Content (from the recording)

## OCR file
REBAR D16 MILL CERTIFICATE — LOT A245 | ← Index
Certificate text (OCR):

## Extract Table
REBAR TENSILE TEST RESULTS — 9-STOREY OFFICE BUILDING | ← Index
Test report No. TN-245/2026 (extracted from the laboratory PDF)

## OCR Screen Clip
CONCRETE MIX-DESIGN TRACKER — 9-STOREY OFFICE BUILDING |  |  |  | ← Index
No. | Element | Grade | Mix proportions per 1 m³
1 | Blinding concrete | B7,5 (M100) | Cement PCB40: 230 kg — Sand: 520 kg — Aggregate 4×6: 900 kg — Water: 175 l
2 | Footings, ground beams | B25 (M350) | Cement PCB40: 390 kg — Sand: 620 kg — Aggregate 1×2: 1170 kg — Water: 190 l
3 | Columns, walls L1–L3 | B25 (M350) | Cement PCB40: 390 kg — Sand: 620 kg — Aggregate 1×2: 1170 kg — Water: 190 l
4 | Beams, slab L3 | B22,5 (M300)

## Batch print
CONSTRUCTION WORK ACCEPTANCE RECORD |  |  |  | ← Index
Element number: | 1 | Sheets: | BBNT+Appendix
Element: | Column C1 — grid A/1, level 3 | File name: | BBNT_Cot_1
Elevation: | +7,200 ÷ +10,800
Concrete grade: | B25 (M350)
Inspection date: | 2026-10-12

## Set page margins
CONSTRUCTION WORK ACCEPTANCE RECORD |  |  |  |  | ← Index
No.: BB-01/NT — Project: 9-storey office building
No. | Work inspected | Unit | Quantity | Result
1 | Level-3 column rebar (grid 1–5) | t | 4.85 | Accepted
2 | Level-3 column formwork | m² | 126.4 | Accepted

## Sheets → PDF
COMPLETED QUANTITIES — PAYMENT 3 |  |  |  |  | ← Index
Project: 9-storey office building
No. | Work item | Unit | Quantity | Note
1 | Level-3 columns, concrete B25 | m³ | 38.6
2 | Level-3 column rebar, CB400-V | t | 6.42
3 | Level-3 column formwork | m² | 312.8

## Send Email
E-MAIL MAILING LIST | [6 empty] | ← Index
1 |  | qlda@congty.vn | ntp.dien@congty.vn | giamsat@congty.vn |  | Inspection: L3 electrical
No. | Send Date | Sender Email | To | Cc | Bcc | Subject
1 |  | qlda@congty.vn | ntp.dien@congty.vn | giamsat@congty.vn |  | Inspection: L3 electrical
2 |  | qlda@congty.vn | ntp.nuoc@congty.vn | giamsat@congty.vn |  | Inspection: L3 plumbing
3 |  | qlda@congty.vn | ntp.nhom@congty.vn | giamsat@congty.vn |  | Inspection: curtain wall

## Email Template
← Index
DANH MỤC GỬI EMAIL
1 |  | qlda@congty.vn | ntp.dien@congty.vn | giamsat@congty.vn |  | Inspection: L3 electrical
No. | Send Date | Sender Email | To | Cc | Bcc | Subject
1 |  | qlda@congty.vn | ntp.dien@congty.vn | giamsat@congty.vn |  | Inspection: L3 electrical
2 |  | qlda@congty.vn | ntp.nuoc@congty.vn | giamsat@congty.vn |  | Inspection: L3 plumbing
3 |  | qlda@congty.vn | ntp.nhom@congty.vn | giamsat@congty.vn |  | Inspection: curtain wall

## Merge to Word
SoBB | TenHangMuc | LyTrinh | NgayNghiemThu | NhaThau | KetLuan | ← Index
BB-01 | Storm drain D600 | Km0+000–050 | 2026-10-05 | Civil crew 1 | Accepted
BB-02 | Storm drain D600 | Km0+050–100 | 2026-10-05 | Civil crew 1 | Accepted
BB-03 | Storm drain D800 | Km0+100–150 | 2026-10-06 | Civil crew 2 | Accepted
BB-04 | Manhole HG-04 | Km0+150 | 2026-10-07 | Civil crew 2 | Accepted
BB-05 | Storm drain D800 | Km0+150–200 | 2026-10-08 | Civil crew 1 | Accepted
BB-06 | Manhole HG-05 | Km0+200 | 2026-10-08 | Civil crew 2 | Accepted

## Create Title
INSPECTION REQUEST LOG — 9-STOREY OFFICE BUILDING | [5 empty] | ← Index
Request No. | Package | Work inspected | Inspection date | Location | Contractor
YC-031 | Structure | Level-3 column rebar | 2026-10-05 | Grid 1–5 | Rebar crew 2
YC-032 | Structure | Level-3 beam & slab formwork | 2026-10-07 | Grid A–D | Formwork crew 1
YC-033 | MEP | Level-3 cast-in conduits | 2026-10-08 | Whole slab | Electrical sub

## Reading Layout
SUPERSTRUCTURE BILL OF QUANTITIES — 9-STOREY OFFICE | [5 empty] | ← Index
No. | Work item | Unit | Quantity | Rate | Amount
1 | Column concrete B30, 1x2 aggregate | m³ | 48.6 | 1912000 | 92923200
2 | Beam concrete B30 | m³ | 86.2 | 1865000 | 160763000
3 | Slab concrete B30 | m³ | 142.5 | 1840000 | 262200000
4 | Column rebar CB400-V, D ≤ 18 | t | 9.84 | 22150000 | 217956000
5 | Beam rebar CB400-V, D ≤ 18 | t | 14.26 | 21980000 | 313434800
6 | Column formwork | m² | 412 | 186500 | 76838000
7 | Beam and slab formwork | m² | 1286 | 172000 | 221192000

## Sheet List
| INTERIM PAYMENT No. 2 — SUMMARY |  |  | ← Index
No. | Work package | Unit | Amount
1 | Foundations | VND | 4856200000
2 | Superstructure | VND | 7312450000
3 | Finishes | VND | 2104800000

## Rename Sheets
Old sheet name | New sheet name | ← Index
Sheet1 | 01-TH-Khoiluong
Sheet2 | 02-KL-Mongcoc
Sheet3 | 03-KL-Dammong
KL than | 04-KL-Than

## Sheet Numbering
COST ESTIMATE — METHOD STATEMENT | ← Index
Project: 9-storey office building
Scope: foundations and superstructure
1. Basis of the estimate
- Approved construction drawings
- Published material prices, September 2026

## UnDiacritics
| STRUCTURAL WORKS — QUANTITY SUMMARY |  |  | ← Index
No. | Item | Unit | Quantity
1 | Pile caps and ground beams, B25 | m³ | 412.6
2 | Foundation rebar CB400-V | t | 38.4
3 | Columns, beams, slabs, B30 | m³ | 1286

## Khối lượng móng
FOUNDATION QUANTITIES |  |  | ← Index
| Total | 412.6

## Đài móng - Cọc
PILE CAPS - PILES | ← Index

## Nghiệm thu thép
REBAR INSPECTION | ← Index

## Phụ lục 01
APPENDIX 01 | ← Index

## Hide Unselected
| PACKAGE XL-02 — ESTIMATE SUMMARY |  | ← Index
No. | Cost item | Amount (VND)
1 | Construction cost | 18426500000
2 | Equipment cost | 2315000000
3 | Contingency | 1037075000

## KL-Mong
FOUNDATION QUANTITIES |  |  | ← Index
| Total | 6218300000

## KL-Than
SUPERSTRUCTURE QUANTITIES |  |  | ← Index
| Total | 12208200000

## DonGia-NoiBo
INTERNAL RATES — not for sending | ← Index

## Chietinh
RATE BREAKDOWN — not for sending | ← Index

## Phuluc
APPENDIX | ← Index

## Nhap1
DRAFT — not for sending | ← Index

## Unhide All
| UNIT RATE SUMMARY |  |  | ← Index
No. | Work item | Unit | Rate (VND)
1 | Foundation concrete B25 | m³ | 1865400
2 | Foundation rebar CB400-V, D ≤ 18 | t | 22150000
3 | Foundation formwork | m² | 186500

## Chietinh-VT (hidden)
MATERIAL RATE BREAKDOWN (hidden sheet) |  |  | ← Index
| Unit rate | 1865400

## Giavatlieu (hidden)
MATERIAL PRICES (hidden sheet) | ← Index

## DonGia-CT (hidden)
DETAILED RATES (hidden sheet) | ← Index

## KL
QUANTITIES | ← Index

## Phuluc (2)
APPENDIX | ← Index

## View Image
SITE PHOTO LOG — WEEK 32/2026 |  |  |  | ← Index
Date | Location | Photo | Remarks
2026-08-05 | Level 5 slab, grids 1–3 | photo | Slab bars Ø10 @150, chairs in place
2026-08-06 | Level 5 slab, grids 3–6 | photo | Add chairs in panel S5-4
2026-08-07 | Beam D5-12, grid B | photo | Accepted, concreting approved

## Hide Empty Rows
VARIATION QUANTITIES — BATCH 3 |  |  |  |  | ← Index
No. | Work item | Unit | Quantity | Remarks
1 | Extra excavation for manholes | m³ | 12.5
2 | Blinding concrete to manholes, M100 | m³ | 1.8
3 | Solid-brick manhole walls, M75 mortar | m³ | 3.2
4 | Manhole wall plaster 2 cm, M75 | m² | 24.6
5 | RC manhole cover 1.0×1.0 m | pcs | 4 | Per site record
| SUPERVISION CONSULTANT |  | CONTRACTOR

## Explain formula (Coach)
MONTHLY CONCRETE QUANTITIES (m3) | [5 empty] | ← Index
TT | Code | Aug 2026 | Sep 2026 | Oct 2026 | Description
1 | BT.M | 142.5 | 96 | 48 | Foundation concrete
2 | BT.C | 0 | 38.4 | 57.6 | Column concrete
3 | BT.S | 0 | 0 | 112.8 | Slab concrete

## Pour log
CONCRETE POUR LOG (m3) — source of the named ranges MaCV, Thang, KhoiLuong |  |  |  | ← Index
Pour date | Item | Month | Volume
2026-08-12 | BT.M | Aug 2026 | 86.5
2026-08-26 | BT.M | Aug 2026 | 56
2026-09-09 | BT.M | Sep 2026 | 96
2026-09-18 | BT.C | Sep 2026 | 38.4
2026-10-07 | BT.M | Oct 2026 | 48
2026-10-14 | BT.C | Oct 2026 | 57.6
2026-10-21 | BT.S | Oct 2026 | 112.8

## Fix formula error
FOUNDATION ESTIMATE | [6 empty] | ← Index
TT | Rate code | Item | Unit | Qty | Unit rate | Amount
1 | BT01 | Blinding concrete M100 | m3 | 18.6 | 1320000 | 24552000
2 | BT02 | Foundation concrete M300 | m3 | 286.5 | 1850000 | 530025000
3 | CT01 | Foundation rebar | t | 34.2 | #N/A | #N/A
4 | VK01 | Foundation formwork | m2 | 236 | 185000 | 43660000

## DonGia
UNIT RATES — FOUNDATIONS |  |  |  | ← Index
Code | Item | Unit | Unit rate
BT01 | Blinding concrete M100 | m3 | 1320000
BT02 | Foundation concrete M300 | m3 | 1850000
CT01 | Foundation rebar | t | 21500000
VK01 | Foundation formwork | m2 | 185000

## Grammar
INSPECTION LOG — 9-STOREY OFFICE BUILDING |  | ← Index
Date | Work description
2026-10-05 | inspection of rebar for beam and slab level 3 , meet requirement
2026-10-06 | formwork erected for column grid A-B ,not cleaned yet
2026-10-07 | footing M1 , M2 concrete poured finish at 16h ,curing by water
2026-10-08 | check level of footing bottom , agree with design

## Solver
OCCUPATIONAL SAFETY TEST REVISION |  | ← Index
Test page | Answers
Page 1 (Q1–10)
Page 2 (Q11–20)

## DVD Chat
FOUNDATION CONCRETE — CHECK AGAINST DRAWINGS | [5 empty] | ← Index
Code | Element | Unit | Calc. qty | Drawing qty | Diff.
M1 | Pile caps M1 (8 no.) | m3 | 96 | 108 | 12
M2 | Pile caps M2 (6 no.) | m3 | 64.8 | 64.8 | 0
GM | Ground beams | m3 | 42.8 | 42.8 | 0