## Inspection log
INSPECTION LOG — 9-STOREY OFFICE BUILDING
Date | Work description
2026-10-05 | inspection of rebar for beam and slab level 3 , meet requirement
2026-10-06 | formwork erected for column grid A-B ,not cleaned yet
2026-10-07 | footing M1 , M2 concrete poured finish at 16h ,curing by water
2026-10-08 | check level of footing bottom , agree with design