## Ke hoach NT 2026-10-08
CONSTRUCTION WORK ACCEPTANCE PLAN
Project: 9-storey office building – Package XL-02 Date: 08/10/2026 Source: schedule 'Schedule'
No. | Code | Work item / acceptance scope | Acceptance type | Applicable standard | Start date | Planned acceptance | Inspection parties | Status | Note
1 | 1.1 | Excavation of footings | Construction work | TCVN 4447:2012 | 2026-10-05 | 2026-10-09 | Client/Supervision consultant; Contractor's technical staff | Pending
2 | 1.2 | Blinding concrete, footings F1–F6 | Construction work | TCVN 4453:1995 | 2026-10-10 | 2026-10-11 | Client/Supervision consultant; Contractor's technical staff | Pending
3 | 1.3 | Footing reinforcement F1–F6 | Construction work | TCVN 4453:1995; TCVN 1651-2:2018 | 2026-10-12 | 2026-10-15 | Client/Supervision consultant; Contractor's technical staff | Pending
4 | 1.4 | Footing formwork F1–F6 | Construction work | TCVN 4453:1995 | 2026-10-14 | 2026-10-16 | Client/Supervision consultant; Contractor's technical staff | Pending
5 | 1.5 | Footing concrete pour F1–F6 | Construction work | TCVN 4453:1995 | 2026-10-17 | 2026-10-17 | Client/Supervision consultant; Contractor's technical staff | Pending
6 | 1.6 | Backfilling of footings | Construction work | TCVN 4447:2012 | 2026-10-20 | 2026-10-22 | Client/Supervision consultant; Contractor's technical staff | Pending