## ITP
INSPECTION AND TEST PLAN (ITP) — FOUNDATIONS
No. | Inspection point | Type
1 | Check pile centre set-out | W
2 | Check pile top level | H
3 | Inspect reinforcement before pouring | H
4 | 28-day compression test | H
5 | Cure pile-cap concrete | W
H = hold point (supervisor must attend); W = witness point