## Foundation schedule
FOUNDATION WORKS SCHEDULE – 9-STOREY OFFICE BUILDING
Activity ID | Activity Name | Duration | Start | Finish
A1010 | Excavate foundation pits | 6 | 2026-10-05 | 2026-10-10
A1020 | Blinding concrete | 2 | 2026-10-12 | 2026-10-13
A1030 | Pile cap rebar and formwork | 8 | 2026-10-14 | 2026-10-22
A1040 | Pile caps, ground beams | 2 | 2026-10-23 | 2026-10-24
A1050 | Backfill, raise ground floor | 6 | 2026-10-26 | 2026-10-31
A1060 | Foundation acceptance | 0 |  | 2026-11-02