## Import 9-storey office building
SCHEDULE — 9-storey office building
Activity ID | Activity Name | Duration | Start | Finish | Predecessors | Complete (%)
A1010 | Excavate foundation pits | 6 | 2026-10-05 | 2026-10-10 |  | 100%
A1020 | Blinding concrete | 2 | 2026-10-12 | 2026-10-13 | A1010FS | 100%
A1030 | Pile cap rebar and formwork | 8 | 2026-10-14 | 2026-10-22 | A1020FS | 40%
A1040 | Pile caps, ground beams | 2 | 2026-10-23 | 2026-10-24 | A1030FS | 0%
A1050 | Backfill, raise ground floor | 6 | 2026-10-26 | 2026-10-31 | A1040FS | 0%