## Site photos
SITE PHOTO LOG — WEEK 41/2026
Project: 9-storey office building
No. | Work item / location | Site photo | Remarks
1 | Rebar fixing, level-3 slab, grid 1-3 |  | Accepted 06/10
2 | Beam formwork, level 3, grid A-B |  | Awaiting supervisor
3 | Concreting footing M3, B25 |  | 2 sample sets taken
4 | External walls, level 2 |  | Passed