## Minutes
WEEKLY SITE MEETING MINUTES — WEEK 41/2026
Project: 9-storey office building
1. | Foundation progress: 85 % of plan.
2. | Supervisor: pile-cap ĐM-4 bottom level on the shop drawing differs from design.
3. | Contractor to check and resubmit before 10/10/2026.
Illustration: