## Progress
PROGRESS TRACKING, WEEK 41 — 9-STOREY OFFICE BUILDING
No. | Task | Planned finish | % done | Legend
1 | Pour level 5 slab concrete | 2026-10-03 | 100% | Behind schedule
2 | Fabricate level 6 beam rebar | 2026-10-08 | 100%
3 | Erect level 6 column formwork | 2026-10-06 | 80%
4 | Level 2 internal plastering | 2026-10-07 | 70%
5 | Level 2 toilet waterproofing | 2026-10-09 | 100%
6 | Level 3 AAC block walls | 2026-10-08 | 45%
7 | Level 2 plumbing pipes | 2026-10-14 | 60%
8 | Level 2 window frames | 2026-10-05 | 30%
Tasks behind schedule